## Slide 1: VHA iEHR Lessons Learned Quarterly Deliverable Reporting Period: April 2014 – June 2014 Task 1.6

## Slide 2: Overview of Lessons Learned
Purpose: Identify and observe iEHR program issues/risks, highlight positive activities and suggest mitigation strategies and actionable recommendations that will inform and enable leadership to more effectively manage VHA involvement in iEHR.
Frequency: Lessons Learned reporting is a quarterly - based deliverable.
Approach: Lessons Learned will answer three basic questions:
  What went right?
  What went wrong?
  How can we improve moving forward?
Follow-up: Review on a quarterly basis will include status of previously reported Lessons Learned.

## Slide 3: Lessons Learned Tracking from FY14-Quarter 2
In FY 14-Quarter 2, we captured 3 lessons learned and developed action items to resolve associated issues as well as to promote observed best-practices.
# | Status | Lesson Learned | Owner | Status:
1 |  | Compliance with FY14 National Defense Authorization Act (NDAA) Interoperability Requirements | VA, DoD, and IPO Interoperability Leads | The Joint Legacy Viewer (JLV) will function as the interim viewer to meet the September 2014 NDAA deadline. In addition to the previous seven data domains that were delivered in December 2013, there were eight data domains where data domain analysis reports were delivered to be displayed in JLV. Another eight data domains are currently underway.
2 |  | Interoperability Resource and Communications Challenges | VA, DoD, and IPO Interoperability Leads | The Joint Information Interoperability Plan (JIIP), Information Interoperability Technical Package (I2TP) and the VistA Evolution Interoperability Plan (VEIP) have been developed as well as consolidated Integrated Master Schedules, Dashboards, and roadmaps. There is an effort to bring these documents together in a more consolidated format.
Incomplete
In-Progress
Complete

## Slide 4: Lessons Learned Tracking from FY14-Quarter 2
In FY 14-Quarter 2, we captured 3 lessons learned and developed action items to resolve associated issues as well as to promote observed best-practices.
# | Status | Lesson Learned | Owner | Status:
3 |  | VHA Clinician Awareness of DoD Data Sharing Capabilities | VHA and OIT Senior Leadership | A recent set of Virtual Lifetime Electronic Record (VLER) Health promotional materials were recently released. A blog posting was released on the Bidirectional Health Information Exchange (BHIE) program.
Incomplete
In-Progress
Complete

## Slide 5: FY14-Q3 Lesson Learned #1: Data Domain Work Processes
Observations: To conform to the NDAA deadline, VA had to analyze a number of data domains to allow for standardized data to be available in the Joint Legacy Viewer (JLV) by the September 30, 2014 deadline. VA experienced some challenges obtaining the discrete data elements used to analyze the prioritized data domains, which resulted in some delays in abiding by the established schedule. The determination of what data was available in the system and how to obtain that data occurred concurrent with the analysis work rather than prior to the establishment of the data domain prioritization list and the establishment of the analysis schedule. Some of the processes and procedures, such as the codification of the four stages of the data domain process, were completed concurrent with the work as well. The VA relied on staffing surges and full day meetings to accomplish the necessary work by the prescribed deadlines, which pulled VA-wide staff from their routine assignments. As a result of these surges, VA submitted a number of analysis reports to the IPO, and a great deal of work was accomplished.
Lesson Learned: VA completed a great deal of work this quarter on its data domain work through the reliance of staffing surges. However, the staffing surges pulled staff from their regular responsibilities. VA would have benefitted from significant advance planning so there would be an equitable distribution of resources.
Recommendation: Work with the ICIB and Health Executive Committee (HEC) to identify the next data domains that are achievable in a realistic timeframe and that have data available in VistA. A strategy and process will also need to be developed for obtaining the data for analysis. This should occur prior to kicking off the work. (VA Leads) Devote adequate resources to the program so that there is dedicated end-to-end availability of staff to support this effort. (VA Leads)

## Slide 6: FY14-Q3 Lesson Learned #2: Lack of Clarity Regarding Funding
Observations: VA continued to face funding restrictions at about 25% of its appropriated level. These restrictions may not be lifted until VA is fully compliant with the NDAA. VA, DoD, and IPO may have provided inconsistent messaging about the status of interoperability as well as compliance with the NDAA. This could have led to an overpromising of products or inconsistent messaging regarding status updates. Clarification may need to be provided on the distinction in potential funding between VE and interoperability. There was also confusion about what funds were released by Congress this quarter. There were some funds released for the Virtual Lifetime Electronic Record (VLER) while some VE and Interoperability funds remained locked. There has been money allocated to achieve ONC EHR certification, but more information is needed. The team did not know if this money was technically allocated to VE, if it was obligated to other product development efforts, or if it genuinely belonged to the ONC EHR certification office.
Lesson Learned: A lack of clarity surrounding funding potentially led to inefficiencies and project delays.
Recommendation: VA, DoD and the IPO will need to have ongoing monitoring of funding, as well as continue to have consistent messaging going forward when interacting with Congressional leaders. (VA Program Leads) VA will need to clarify current budget allocations. (VA Program Leads)

## Slide 7: FY14-Q3 Lesson Learned #3: Communications about Organizational Changes
Observations: To adapt to the changing environment and landscape that is more interoperability focused, the iEHR staff Office was renamed and started shifting its focus as the Health Systems Management Office. The name change reflects the Departments moving away from an integrated electronic health record towards interoperability. Concurrently, the former DoD/VA Health Information Sharing Office continues to change and adapt as the Interoperability Office. The office is currently working on issues such as data domain work, data sharing, and VLER. The announcement about these changes seemed to be somewhat piecemeal and through a number of different meetings rather than one direct announcement. Staff were sometimes unaware of the changes that had occurred.
Lesson Learned: Offices should be aware of changes in the evolving landscape and reshape accordingly. Offices should engage in consistent messaging to keep staff and stakeholders apprised of these changes.
Recommendation: Adapt and change to the evolving Health IT sector. Ongoing and regular communication across stakeholders and staff members should occur to keep staff apprised of ongoing changes. (VA Staff Offices)

## Slide 8: FY14-Q3 Lesson Learned #4: Proliferation of Interoperability-related Documentation
Observations: There are a number of documents generated internal to VA, through DoD and the IPO related to interoperability. Some of these documents include the Health Data Information Management Plan, the VistA Evolution Interoperability Plan, the Interoperability Executive Summary, the Joint Interoperability Information Plan, the Information Interoperability Technical Package, roadmaps, timelines, Work Breakdown Structures, Dashboards, Integrated Master Schedules, and Integrated Master Plans.
Lesson Learned: The circulation of these documents has led to confusion about the purposes of these documents, and a duplication of effort. There also needs to be a better understanding of what documents are owned by the VA and what is external to VA. For some documents, it can be unclear what each document is intended to accomplish.
Recommendation: The documentation needs to be matrixed for an understanding of document purpose, goal, deadline, document owner. The existing documents should be leveraged to populate new requests for information. (VA Staff Offices)

## Slide 9: Lessons Learned – FY14-Quarter 3 Recap
# | Lesson Learned | Recommended Actions to be Completed by Next Reporting Period
1 | Data Domain Work Processes | Work with the ICIB and Health Executive Committee (HEC) to identify the next data domains that are achievable in a realistic timeframe and that have data available in VistA. A strategy and process will also need to be developed for obtaining the data for analysis. This should occur prior to kicking off the work. Devote adequate resources to the program so that there is dedicated end-to-end availability of staff to support this effort
2 | Lack of Clarity Regarding Funding | VA, DoD and the IPO will need to have ongoing monitoring of funding, as well as continue to have consistent messaging going forward when interacting with Congressional leaders. VA will need to clarify current budget allocations.
3 | Communications about Organizational Changes | Adapt and change to the evolving Health IT sector. Ongoing and regular communication across stakeholders and staff members should occur to keep staff apprised of ongoing changes.
4 | Proliferation of Interoperability-related Documentation | The documentation needs to be matrixed for an understanding of document purpose, goal, deadline, document owner. The existing documents should be leveraged to populate new requests for information.

## Slide 10
Back-Up Slides

## Slide 11: FY14-Q2 Lesson Learned #1: Compliance with FY14 National Defense Authorization Act (NDAA) Interoperability Requirements
Observations: On February 25, VHA Interoperability Office leadership met with OIT, IPO, and DoD Interoperability leads to identify key points of contact on all sides and to discuss the overarching roadmap to achieve health data interoperability between the Departments. The group unanimously agreed that the Departments will not be able to deliver computable data interoperability (semantic interoperability) for all identified data domains by October 2014, a requirement of the FY14 NDAA. During the March 18 Interagency Clinical Informatics Board (ICIB) meeting, it was relayed to DoD and VA middle management that the October 1, 2014 Interoperability delivery deadline is not going to be met as originally expected by Congress and Department Senior Leadership. During the March 19 Health Informatics and Technology Roundtable, VHA physicians emphasized the need to develop interoperability solutions that will most positively impact and assist VA and DoD clinicians’ ability to provide the best medical care to Veterans and Servicemembers. It was noted that this level of interoperability may be at a lower level than what is stated in the NDAA.
Lesson Learned: The Interoperability delivery timeline stated in the FY14 NDAA is unrealistic given the desired scope. While it is clear that VA and DoD are committed to achieving health data interoperability, the resources available to each Department for interoperability efforts in the short-term are limited. Additionally, the NDAA’s more limited scope will achieve the desired outcome.
Recommendation: Work with the ICIB to create a realistically achievable interoperability delivery scope and timeline that takes into account VA/DoD clinician needs and available staffing resources. Submit this new approach to VA and DoD leadership for proper dissemination to proper authorities (VA, DoD, and IPO Interoperability Leads)

## Slide 12: FY14-Q2 Lesson Learned #2: Interoperability Resource and Communications Challenges
Observations: While VA/DoD Interoperability has been confirmed and committed to by the Departments for nearly six months, both Departments at leadership and management levels have experienced difficulties effectively communicating ideas and developing a comprehensive and inclusive Interoperability execution plan. VA is currently working to identify data domain SMEs and determine the amount of data domain squads that can be supported concurrently. DoD has expressed its inability to provide immediate technical data mapping support due to the lack of a support contract. During the development of the James A. Lovell Federal Health Care Center Transition Plan, the Health Information Exchange Requirements Document to the Health Executive Committee (HEC), and the Joint Information Interoperability Plan, collaboration between VA and DoD authors and reviewers was minimal. This resulted in the documents being developed independently by one Department and last-minute scrambles to have required input included.
Lesson Learned: VA, DoD, and the IPO are continually challenged to effectively work together on Congressionally mandated efforts and develop required joint deliverables in a collaborative fashion. While it is clear that VA and DoD are committed to achieving health data interoperability, the resources available to each Department for interoperability efforts in the short-term are limited.
Recommendation: Complete the Joint Information Interoperability Plan and brief to Congress as soon as possible. This will demonstrate a united leadership and management approach between VA and DoD, help manage Congress’ expectations on realistic delivery timelines, and potentially help remove the funding restriction on VA and DoD EHR development efforts. (VA, DoD, and IPO Interoperability Leads)

## Slide 13: FY14-Q2 Lesson Learned #3: VHA Clinician Awareness of DoD Data Sharing Capabilities
Observations: On the February 19 Health Informatics and Technology Roundtable meeting, it was announced that many VHA clinicians and VAMC leadership (including Chiefs of Staff, Chief Medical Information Officers, and Clinical Applications Coordinators) are unaware of the capability to view DoD patient records via BHIE and JLV (where available). BHIE has been in existence for many years and training material is available to all VAMC CACs. There is a high turnover rate of staff at facilities, leading to a gap in knowledge between (current and former?) staff members.
Lesson Learned: Despite the available software technology and training forums available, many VHA clinicians are unaware of the capability to view DoD patient records. Education and training materials supporting this functionality should be regularly circulated to all VAMC leadership and clinicians to ensure providers have access to the most comprehensive set of patient data available.
Recommendation: Update all BHIE and JLV training materials. Distribute training materials on proper communications forums and directly to all VAMC Chiefs of Staff, Chief Medical Information Officers, and CACs on an annual basis or when ever new staff are employed (VA Chief Health Information Officer and Communications Support Staff) Circulate updated BHIE and JLV training materials to all VHA clinicians on an annual basis to remind staff and educate new employees about available resources to view DoD patient information. (VAMC CACs)