## Slide 1: Veterans Health & Interoperability Exchange (VHIEx) Integrated Business Team (IBT) Meeting
April 29, 2014

## Slide 2: Agenda
Review and Discussion
  Program Accelerators
  Veteran Access
Wrap Up
  Next Steps/Action Items

## Slide 3: VLER Health Program Accelerated Goals
Exchange
150,000 authorized Veterans by 1QFY2015; 1,000,000 authorized Veterans by 1QFY2016
130 non-VA partners by 1QFY2016
85% Records Matched
Direct
Add 20 Direct Partners by end of Q1FY2015
Register 250 VA Direct Users by end of Q1FY2015; transmit 2,000 Direct provider-to-provider messages by Q1FY2015
Community Health Information Exchange
Add 1 Health Information Handler (HIH) Partner by Q1FY2015
Add 7 additional HIHs by the end of FY2015
Support Community HIEs at 20 sites by end of Q4 FY2015

## Slide 4: Acceleration Plan: Locks and Keys
Locks | Actions | Target Completion Date/Status | Issues | Status | Responsible
Veteran recruitment and authorizations | Paradigm shift from "Opt-in" to "Opt-out" model | N/A | Authorization process is tedious, slow, and not scalable. |  | 
 | Obtain selective authorizations by parsing out data for 7332 (“confidentiality of certain medical records”) conditions | Q4CY14 | Authorization process is tedious, slow, and not scalable. |  | 
 | Promote eBenefits enrollment or registration, kiosk enrollment and include enrollment as part of Veterans’ Point of Services (VPS) applications | Date pending analysis | Authorization process is tedious, slow, and not scalable. | Next steps: engage with eBenefits for improvements to enrollment/registration, engage with VPS for kiosk applications. Authentication/identity issues current being discussed | 
Information Technology Issues | Ensure that systems are fully compliant with all applicable security and functional organization requirements | Q4CY14 | Compliant systems |  | 
Provider Usage/Adoption | Meet with Initiate (IBM), and MVI, to discuss matching algorithms and configurability |  | Identity Matching rate is low | Pending | 
 | Hire staff dedicated to manual analysis of failed matches (4 FTEs) |  | Identity Matching rate is low | External: hiring within MVI | 
Policy/Governance | Allow implementation policy exemptions/trial-based policy exemptions |  | VA policy approval takes too long | Develop exemptions on a trial/situational basis | 
 | Allow implementation policy exemptions/trial based policy exemptions | Q4FY14 | Policy development process is lengthy | Develop exemptions on a trial/situational basis | 

## Slide 5: Acceleration Plan: Locks and Keys
Locks | Actions | Target Completion Date/Status | Issues | Status | Responsible
EXTERNAL: Allow Veterans to sign authorizations through MHV | Install Veteran sign up for VLER Health | Q4CY14 | Veterans signed up through MHV | Need commitment and schedule from MHV; email from Theresa Hancock (dated May 12) on FICAM compliance. Awaiting for FICAM certification | 
 | Meet Federal Identity, Credential, and Access Management (FICAM) certification | Q4CY14 | Veterans signed up through MHV |  | 
 | Access VLER Health authorization forms in Veterans Authorizations and Preferences (VAPii) application | Q4FY14 | Veterans signed up through MHV; MHV and VAPii need to be able to connect (interface) - VAP needs to know a patient is authorized |  | 
 | Advertise VLER Health and provide sign up opportunity | Q4CY14 | Veterans signed up through MHV |  | 

## Slide 6: Veteran Access Activities
Activities | Tasks
Veteran Engagement Activities | Enable external partners to collect consent for us and send consent acknowledgement
 | Build checkbox within patients' charts
 | Paradigm shift from "Opt-in" to "Opt-out" model
 | Obtain selective authorizations by parsing out data for 7332 (“confidentiality of certain medical records”) conditions
 | Implement 7332 workaround
 | Promote eBenefits enrollment or registration, kiosk enrollment and include enrollment as part of Veterans’ Point of Services (VPS) applications
 | Re-evaluate approve to Veteran Authorization
 | Recruit Veterans at points of encounter
 | Integration authorizations into Veteran applications
 | Ensure communications to target audiences
 | Conduct community outreach; attend VSO functions
Policy Governance Activities | Allow implementation policy exemptions/trial-based policy exemptions
 | Streamline governance processes for approval and decision
 | Allow implementation policy exemptions/trial based policy exemptions
 | Determine policy for security and privacy agreements
 | Determine policy for Veteran Initiated messaging; set up system to support policy
 | Streamline communication processes
 | Extend DURSA to all of VA
Authorization through MHV Activities | Install Veteran sign up for VLER Health
 | Meet Federal Identity, Credential, and Access Management (FICAM) certification
 | Access VLER Health authorization forms in Veterans Authorizations and Preferences (VAPii) application
 | Advertise VLER Health and provide sign up opportunity
External Health Information Exchange Activities | Standing up Triwest with Direct Access
 | Expand other HIEs to support Purchase Care
 | Stand up HIHs for providers who don’t have Direct
 | Standup community exchanges as needed
 | Extend current HIE authorization language to all HIE (Privacy) – get OGC and OMB approval

## Slide 7: Wrap Up
Next Steps/Action Items