1. SOLICITATION NUMBER

2. TYPE OF SOLICITATION

3. DATE ISSUED

PAGE OF PAGES

4. CONTRACT NUMBER

5. REQUISITION/PURCHASE REQUEST NUMBER

6. PROJECT NUMBER

7. ISSUED BY

CODE

8. ADDRESS OFFER TO

a. NAME

b. TELEPHONE NUMBER (Include area code) (NO COLLECT CALLS)

10. THE GOVERNMENT REQUIRES PERFORMANCE OF THE WORK DESCRIBED IN THESE DOCUMENTS (Title, identifying number, date)

12a. THE CONTRACTOR MUST FURNISH ANY REQUIRED PERFORMANCE AND PAYMENT BONDS?

(If "YES," indicate within how many calendar days after award in Item 12B.)

12b. CALENDAR DAYS

13. ADDITIONAL SOLICITATION REQUIREMENTS:

STANDARD FORM 1442 (REV. 8/2014)

STANDARD FORM 1442

Prescribed by GSA-FAR (48 CFR) 52.236-1(d)

SOLICITATION, OFFER,

AND AWARD

(Construction, Alteration, or Repair)

SOLICITATION

SOLICITATION

IMPORTANT - The "offer" section on the reverse must be fully completed by offeror.

9. FOR INFORMATION

 CALL:

NOTE: In sealed bid solicitations "offer" and "offeror" mean "bid" and "bidder".

SEALED BID (IFB)

NEGOTIATED (RFP)

11. The Contractor shall begin performance within \_\_\_\_\_\_\_\_\_\_\_\_ calendar days and complete it within

 \_\_\_\_\_\_\_\_\_\_\_\_

calendar days after receiving

award,

notice to proceed. This performance period is

mandatory

negotiable. (See \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).

YES

NO

a.

Sealed offers in original and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_copies to perform the work required are due at the place specified in Item 8 by \_\_\_\_\_\_\_\_\_\_\_\_\_

(hour) local time \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (date). If this is a sealed bid solicitation, offers must be publicly opened at that time. Sealed

envelopes containing offers shall be marked to show the offeror's name and address, the solicitation number, the date and time offers are due.

b.

An offer guarantee

is,

is not required.

c.

All offers are subject to the (1) work requirements, and (2) other provisions and clauses incorporated in the solicitation in full text or by reference.

 .

d.

Offers providing less than \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ calendar days for Government acceptance after the date offers are due will not be

considered and will be rejected.

1 of 85

VA786-17-R-0663

X

8-08-2017

8187-000036

818-NRM17-07

43C1

Department of Veterans Affairs

NCA Contracting Service

75 Barrett Heights Rd. Suite 309

Stafford VA 22556

Department of Veterans Affairs

NCA Contracting Service

75 Barrett Heights Rd. Suite 309

Stafford VA 22556

Henry Dukes

540-658-7222

Contractor shall furnish all tools, labor, materials, equipment, services, and professional design services to perform work

described in the SOW, in other specification sections, and on the drawings at Togus National Cemetery as required by project

documents.

**NAICS CODE: 236220 Size Standard: $36.5 Million**

**Magnitude of Construction: Below $150,000.00**

Note: Contractor is strongly encouraged to survey the project area prior to bidding to adequately understand the full

scope of work and all requirements. Contractor is required to submit any questions or clarifications prior to bid. A

bid submitted will be taken as agreement that the work shall be performed to meet the requirements herein based on the

existing conditions in the field.

**THIS PROCUREMENT IS A 100% SMALL BUSINESS SET-ASIDE USING THE CASCADING SET-ASIDE PROCEDURES: 1st Tier SDVOSB, 2nd Tier VOSB,**

**3rd Tier All Other Small Businesses.**

**There will be Two (2) Pre-bid Site Inspections on: Tuesday, 15 August 2017 at 9:00 AM and Wednesday,16 August 2017 at 9:00** AM.

**Cemetery POC: John Spruyt, Cemetery Director, Phone No: (508) 563-7113 or by e-mail: John.Spruyt@va.gov (to schedule visit**).

**No Bid Bonds are required**. **Payment and Performance Bonds are Required as Contractor chooses in 52.228-13.**

All proposals must be submitted through the Department of Veterans Affairs - Electronic Management System (eCMS) Vendor

Portal website in order to be considered for award. https://www.vendorportal.ecms.va.gov. Please go to

https://www.vendorportal.ecms.va.gov to register. Submission of proposals through email will not be accepted. Proposal

transmission/uploads must be complete by the date/time specified. Late or incomplete proposals will not be considered.

**NOTE:** **If Contractors encounter problems uploading proposals into Vendor Portal – email proposals to:** **henry.dukes@va.gov**

**Or mail a CD that contains the bid proposal package to: Henry C. Dukes, National Cemetery Administration, 75 Barrett**

**Heights Road, Suite 309, Stafford, VA 22556**

Questions shall be emailed to: henry.dukes@va.gov by 2:00 P.M. EST on 08/22/2017.

Contractor Office Telephone:

Contractor Cell #:

Contractor DUNS #:

Contractor Email:

**Proposals Due: 08/29/2017 @ 2:00 P.M. EST**

 14

180

X

X

52.211-10

1

2:00 P.M. EST

08-29-2017

X

60

14. NAME AND ADDRESS OF OFFEROR

15. TELEPHONE NUMBER

16. REMITTANCE ADDRESS

CODE

FACILITY CODE

17. The offeror agrees to perform the work required at the prices specified below in strict accordance with the terms of the solicitation, if this offer is

accepted by the Government in writing within \_\_\_\_\_\_\_\_\_\_ calendar days after the date offers are due.

AMOUNTS

18. The offeror agrees to furnish any required performance and payment bonds.

19. ACKNOWLEDGMENT OF AMENDMENTS

AMENDMENT

NUMBER

DATE.

20a. NAME AND TITLE OF PERSON AUTHORIZED TO SIGN OFFER

20b. SIGNATURE

20c. OFFER DATE

21. ITEMS ACCEPTED:

22. AMOUNT

23. ACCOUNTING AND APPROPRIATION DATA

24. SUBMIT INVOICES TO ADDRESS SHOWN IN

ITEM

25. OTHER THAN FULL AND OPEN COMPETITION PURSUANT TO

10 U.S.C. 2304(c)(

 )

41 U.S.C. 3304(a) (

 )

26. ADMINISTERED BY

27. PAYMENT WILL BE MADE BY

PHONE:

FAX:

28. NEGOTIATED AGREEMENT

29. AWARD

Your

Contractor agrees

offer on this solicitation is hereby accepted as to the items listed. This

to furnish and deliver all items or perform all work requirements identified

award consummates the contract, which consists of (a) the Government

on this form and any continuation sheets for the consideration stated in

solicitation and your offer, and (b) this contract award. No further cont-

this contract. The rights and obligations of the parties to this contract

ractual document is necessary.

shall be governed by (a) this contract award, (b) the solicitation, and (c)

the clauses, representations, certifications, and specifications incorporated

by reference in or attached to this contract.

30a. NAME AND TITLE OF CONTRACTOR OR PERSON AUTHORIZED

31a. NAME OF CONTRACTING OFFICER

TO SIGN

30b. SIGNATURE

30c. DATE

31b. UNITED STATES OF AMERICA

31c. AWARD DATE

BY

**OFFER**

**AWARD**

**STANDARD FORM 1442 (REV. 8/2014) BACK**

(Include ZIP Code)

(Include area code)

(Include only if different than Item 14.)

(Insert any number equal to or greater than

the minimum requirement stated in Item 13d. Failure to insert any number means the offeror accepts the minimum in Item 13d.)

(The offeror acknowledges receipt of amendments to the solicitation -- give number and date of each)

(Type or print)

(4 copies unless otherwise specified)

(Type or print)

(Type or print)

(Contractor is required to sign this

document and return \_\_\_\_\_\_\_ copies to issuing office.)

(Contractor is not required to sign this document.)

**(Must be fully completed by offeror)**

**(To be completed by Government)**

**CONTRACTING OFFICER WILL COMPLETE ITEM 28 OR 29 AS APPLICABLE**

43C1

Department of Veterans Affairs

NCA Contracting Service

75 Barrett Heights Rd. Suite 309

Stafford VA 22556

Department of Veterans Affairs

Financial Services Center

P.O. Box 149971

www.tungsten-network.com/customer-campai

AIRS/ TX 78714-8971

Table of Contents

[SF 1442 SOLICITATION, OFFER, AND AWARD (Construction, Alteration, or Repair) 1](#_Toc256000002)

SECTION A - CONTRACT ADMINISTRATION………………………………………………………..6

[A.1 PRICE/COST SCHEDULE](#_Toc256000003) 9

SECTION B - DESCRIPTION /SPECIFICATION / STATEMENT OF WORK………………………..10

[INFORMATION REGARDING BIDDING MATERIAL, BID GUARANTEE AND BONDS 13](#_Toc256000005)

[1.1 52.228-5 INSURANCE—WORK ON A GOVERNMENT INSTALLATION (JAN 1997) 13](#_Toc256000006)

[1.2 52.228-13 ALTERNATIVE PAYMENT PROTECTIONS (JULY 2000) 13](#_Toc256000007)

[1.3 SUPPLEMENTAL INSURANCE REQUIREMENTS 14](#_Toc256000008)

[INSTRUCTIONS, CONDITIONS AND OTHER STATEMENTS TO BIDDERS/OFFERORS 14](#_Toc256000009)

[2.1 52.212-1 INSTRUCTIONS TO OFFERORS—COMMERCIAL ITEMS (OCT 2016) 14](#_Toc256000010)

[2.2 52.212-2 EVALUATION—COMMERCIAL ITEMS (OCT 2014) 21](#_Toc256000011)

[2.3 LIMITATIONS ON SUBCONTRACTING-- MONITORING AND COMPLIANCE (JUN 2011) 25](#_Toc256000012)

[2.4 52.252-1 SOLICITATION PROVISIONS INCORPORATED BY REFERENCE (FEB 1998) 25](#_Toc256000013)

[2.5 52.209-7 INFORMATION REGARDING RESPONSIBILITY MATTERS (JUL 2013) 26](#_Toc256000014)

[2.6 52.216-1 TYPE OF CONTRACT (APR 1984) 27](#_Toc256000015)

[2.7 52.222-5 CONSTRUCTION WAGE RATE REQUIREMENTS—SECONDARY SITE OF THE WORK (MAY 2014) 27](#_Toc256000016)

[2.8 52.222-23 NOTICE OF REQUIREMENT FOR AFFIRMATIVE ACTION TO ENSURE EQUAL EMPLOYMENT OPPORTUNITY FOR CONSTRUCTION (FEB 1999) 28](#_Toc256000017)

[2.9 52.225-10 NOTICE OF BUY AMERICAN REQUIREMENT—CONSTRUCTION MATERIALS (MAY 2014) 2](#_Toc256000018)9

[2.10 52.233-2 SERVICE OF PROTEST (SEP 2006)](#_Toc256000019) 30

[2.11 VAAR 852.252-70 SOLICITATION PROVISIONS OR CLAUSES INCORPORATED BY REFERENCE (JAN 2008)](#_Toc256000020) 30

[2.12 VAAR 852.233-70 PROTEST CONTENT/ALTERNATIVE DISPUTE RESOLUTION (JAN 2008)](#_Toc256000021) 31

[REPRESENTATIONS AND CERTIFICATIONS 32](#_Toc256000022)

[3.1 52.203-98 PROHIBITION ON CONTRACTING WITH ENTITIES THAT REQUIRE CERTAIN INTERNAL CONFIDENTIALITY AGREEMENTS—REPRESENTATION (DEVIATION) (FEB 2015) 32](#_Toc256000023)

[3.2 52.209-5 REPRESENTATION BY CORPORATIONS REGARDING AN UNPAID TAX LIABILITY OR A FELONY CONVICTION UNDER ANY FEDERAL LAW (DEVIATION)(MAR 2012) 32](#_Toc256000024)

[3.3 52.204-8 ANNUAL REPRESENTATIONS AND CERTIFICATIONS (DEC 2016) 33](#_Toc256000025)

[GENERAL CONDITIONS 37](#_Toc256000026)

[4.1 SBA ACT 8 (d) (13) (B) 37](#_Toc256000027)

[4.2 DIGNITY CLAUSE FOR NCA CONTRACTS 37](#_Toc256000028)

[4.3 52.252-2 CLAUSES INCORPORATED BY REFERENCE (FEB 1998)](#_Toc256000029) 38

[4.4 52.203-99 PROHIBITION ON CONTRACTING WITH ENTITIES THAT REQUIRE CERTAIN INTERNAL CONFIDENTIALITY AGREEMENTS (DEVIATION) (FEB 2015) 41](#_Toc256000030)

[4.5 52.204-19 INCORPORATION BY REFERENCE OF REPRESENTATIONS AND CERTIFICATIONS (DEC 2014) 42](#_Toc256000031)

[4.6 52.217-9 OPTION TO EXTEND THE TERM OF THE CONTRACT (MAR 2000) 42](#_Toc256000032)

[4.7 52.219-28 POST-AWARD SMALL BUSINESS PROGRAM REREPRESENTATION (JUL 2013) 42](#_Toc256000033)

[4.8 52.222-30 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (NONE OR SEPARATELY SPECIFIED METHOD) (MAY 2014) 44](#_Toc256000034)

[4.9 52.222-31 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (PERCENTAGE METHOD) (MAY 2014) 44](#_Toc256000035)

[4.10 52.222-32 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (ACTUAL METHOD) (MAY 2014) 45](#_Toc256000036)

[4.11 52.222-35 EQUAL OPPORTUNITY FOR VETERANS (OCT 2015) 46](#_Toc256000037)

[4.12 52.222-42 STATEMENT OF EQUIVALENT RATES FOR FEDERAL HIRES (MAY 2014) 47](#_Toc256000038)

[4.13 52.225-9 BUY AMERICAN—CONSTRUCTION MATERIALS (MAY 2014) 4](#_Toc256000039)7

[4.14 52.225-11 BUY AMERICAN—CONSTRUCTION MATERIALS UNDER TRADE AGREEMENTS (OCT 2016)](#_Toc256000040) 50

[4.15 52.236-27 SITE VISIT (CONSTRUCTION) (FEB 1995) ALTERNATE I (FEB 1995) 54](#_Toc256000041)

[4.16 VAAR 852.203-70 COMMERCIAL ADVERTISING (JAN 2008) 54](#_Toc256000042)

[4.17 VAAR 852.203-71 DISPLAY OF DEPARTMENT OF VETERAN AFFAIRS HOTLINE POSTER (DEC 1992) 55](#_Toc256000043)

[4.18 VAAR 852.211-74 LIQUIDATED DAMAGES (JAN 2008) 55](#_Toc256000044)

[4.19 VAAR 852.219-10 VA NOTICE OF TOTAL SERVICE-DISABLED VETERAN-OWNED SMALL BUSINESS SET-ASIDE (JUL 2016)(DEVIATION) 55](#_Toc256000045)

[4.20 VAAR 852.228-70 BOND PREMIUM ADJUSTMENT (JAN 2008) 56](#_Toc256000046)

[4.21 VAAR 852.232-72 ELECTRONIC SUBMISSION OF PAYMENT REQUESTS (NOV 2012) 5](#_Toc256000047)6

[4.22 VAAR 852.236-71 SPECIFICATIONS AND DRAWINGS FOR CONSTRUCTION (JUL 2002) 5](#_Toc256000048)8

[4.23 VAAR 852.236-72 PERFORMANCE OF WORK BY THE CONTRACTOR (JUL 2002) 5](#_Toc256000049)8

[4.24 VAAR 852.236-74 INSPECTION OF CONSTRUCTION (JUL 2002) 5](#_Toc256000050)9

[4.25 VAAR 852.236-76 CORRESPONDENCE (APR 1984) 5](#_Toc256000051)9

[4.26 VAAR 852.236-77 REFERENCE TO "STANDARDS" (JUL 2002) 5](#_Toc256000052)9

[4.27 VAAR 852.236-78 GOVERNMENT SUPERVISION (APR 1984) 5](#_Toc256000053)9

[4.28 VAAR 852.236-79 DAILY REPORT OF WORKERS AND MATERIAL (APR 1984)](#_Toc256000054) 60

[4.29 VAAR 852.236-80 SUBCONTRACTS AND WORK COORDINATION (APR 1984)](#_Toc256000055) 60

[4.30 VAAR 852.236-82 PAYMENTS UNDER FIXED-PRICE CONSTRUCTION CONTRACTS (WITHOUT NAS) (APR 1984)](#_Toc256000056) 60

[4.31 VAAR 852.236-84 SCHEDULE OF WORK PROGRESS (NOV 1984) 63](#_Toc256000057)

[4.32 VAAR 852.236-85 SUPPLEMENTARY LABOR STANDARDS PROVISIONS (APR 1984) 64](#_Toc256000058)

[4.33 VAAR 852.236-86 WORKER'S COMPENSATION (JAN 2008) 64](#_Toc256000059)

[4.34 VAAR 852.236-88 CONTRACT CHANGES--SUPPLEMENT (JUL 2002) 64](#_Toc256000060)

[4.35 VAAR 852.236-89 BUY AMERICAN ACT (JAN 2008)](#_Toc256000061) 66

[4.36 VAAR 852.236-91 SPECIAL NOTES (JUL 2002)](#_Toc256000062) 67

[4.37 VAAR 852.246-74 SPECIAL WARRANTIES (JAN 2008)](#_Toc256000063) 67

[SECTION D – CONTRACT DOCUMENTS, EXHIBITS, OR ATTACHMENTS 6](#_Toc256000064)9

 [4.38 ATTACHMENT 1 - CONSTRUCTION WAGE RATES](#_Toc256000065) 70

 4.39 ATTACHMENT 2 - PAST PERFORMANCE QUESTIONNAIRE……………………….75

 4.40 ATTACHMENT 3 - CONTRACTOR PRODUCTION REPORT ………………………...77

 4.41 ATTACHMENT 4 - CONTRACTOR QUALITY CONTROL REPORT…………………80

 4.42 ATTACHMENT 5 - CONTRACTOR DISCREPANCY REPORT ……………………….84

 **SECTION A. CONTRACT ADMINISTRATION**

All contract administration matters will be handled by the following:

**CONTRACTOR:**

**GOVERNMENT**:

Department of Veterans Affairs

National Cemetery Administration

Contracting Service (43C1)

75 Barrett Heights Road, Suite 309

Stafford, VA 22556

1. **CONTRACTOR REMITTANCE ADDRESS:** All payments by the Government to the contractor will be made in accordance with:

 [X] 52.232-34, Payment by Electronic Funds Transfer - Other Than System for Award

 Management

1. **INVOICES:**
2. Invoices shall be submitted in arrears for cumulative work performed no more frequently than weekly within thirty (30) calendar days after the contractor has completed the work and the Government has accepted the items / services rendered.
3. Invoices shall be submitted electronically.
4. Contractors shall not invoice for single orders of a shipment. Shipments will be invoiced for the complete shipment when completed and accepted by the Government.
5. Required Contents of Invoice: If any information below is missing from an invoice, the invoice shall be subject to being rejected and returned for revision.
* Contractor Information (Name, Complete Address, Telephone Number)
* Date of Invoice
* Unique Invoice Number
* Each invoice may be submitted only once. If the need exists to submit a corrected invoice, the original invoice number should be noted with “COR” added at the end of the invoice number on the revised invoice. Where possible, CORRECTED INVOICE shall be clearly noted
* Contract / Purchase Order Number (Only one contract / purchase order may be included on each invoice submitted)
* Shipment Number (If there is not enough space on an invoice, an attachment to the invoice shall list the Shipment Number(s)
* Cemetery Name
* Unit Cost
* Total Dollar Amount Invoiced
* Certificate of Conformance
* This certifies that (Contractor’s Name) furnished the above listed supplies or services called for by the above listed purchase order number in accordance with all applicable requirements. We further certify that the supplies or services are the quality specified and conform in all respects with the contract requirements.
1. **GOVERNMENT INVOICE ADDRESS:** All invoices from the contractor shall be submitted electronically in accordance with VAAR Clause 852.232-72 Electronic Submission of Payment Requests.

Department of Veterans Affairs

Financial Services Center (FSC)

P.O. Box 149971

Austin, Texas 78714

[www.tungsten-network.com/customer-campaiAIRS/](http://www.tungsten-network.com/customer-campaiAIRS/)

1. **SOLICITATIONS:** Proposals for furnishing the supplies or services in the Schedule will be received at the address specified in Block 9 of SF 1449, or if hand carried, to the address shown in block 9, until the date and time specified in Block 8. CAUTION - LATE Submissions, Modifications, and Withdrawals: See provision 52.212-1. All offers are subject to all terms and conditions of this solicitation.

**Pre-Bid Site Visit:** Bidders are strongly urged to inspect, site investigate by observation, and Request for Information (RFI) and responses through the Contracting Office to satisfy their understanding of the work to be done, all general, local and technical conditions that may affect the cost and the feasibility of their proposal. In no event shall failure to inspect the site constitute grounds for a claim after award. Visitors planning to conduct a site visit.

There will be Two (2) Pre-bid Site Inspection scheduled on: Tuesday, 15 August 2017 at 9:00 AM and Wednesday, 16 August 2017 at 9:00 AM. Cemetery POC(s): John Spruyt, Massachusetts National Cemetery Director...............Phone No. 508-563-7113 or by e-mail: John.Spruyt@va.gov

The pre-award question and answer period commences on August 8, 2017 and concludes on August 22, 2017 by 2:00 p.m. (EST). Email questions to henry.dukes@va.gov

1. **ACKNOWLEDGEMENT OF AMENDMENTS:**

 The offeror acknowledges receipt of amendments to the Solicitation numbered and dated as

 follows:

|  |  |
| --- | --- |
| **AMENDMENT NUMBER** | **DATE** |
|  |  |
|  |  |
|  |  |

1. **MISSING PAGES:** It is the responsibility of the offeror to examine this solicitation to verify that he or she has received all pages. In addition, in compiling this package, some pages may have been duplicated. If the offeror feels that pages are missing or duplicated, the offeror is encouraged to contact the Contracting Officer at the telephone number shown in Block 7B, Standard Form 1449, Solicitation / Contract / Order for Commercial Items.
2. **ORDER PROCESSING SEQUENCE:** The Department of Veterans Affairs, National Cemetery Administration, Contracting Service (43C1), is the only activity authorized to issue orders under this contract.
3. **NOTICE TO PROSPECTIVE CONTRACTOR(S):** Prospective awardees **MUST** be registered with the System for Award Management (SAM )at <http://www.sam.gov> , **PRIOR TO AWARD** and through final payment, and must complete the Online Representations and Certifications Application (ORCA) at <http://www.sam.gov> prior to award and through final payment. **CONTRACT WILL NOT BE AWARDED UNTIL SAM REGISTRATION HAS BEEN COMPLETED.** This is a 100% SDVOSB set-aside. Therefore, prospective awardees **MUST** also be registered within the Vendor Information Pages (VIP) and the Verification Case Management System (VCMS) via [www.vip.vetbiz.gov](http://www.vip.vetbiz.gov) (VetBiz.Gov) **PRIOR TO AWARD.**

##

## A.1 PRICE/COST SCHEDULE

|  |  |  |  |
| --- | --- | --- | --- |
| **DESCRIPTION** | **QTY** | **UNIT** | **TOTAL PRICE** |
| Contractor shall provide all labor, tools, materials, equipment, and supervision necessary to perform all work detailed above, in specifications, and drawings at Togus National Cemetery. | 1 | JOB | $ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

**The place of performance for this requirement will be located at the following:**

Togus National Cemetery, VA Medical and Regional Office Center

810 Eastern Avenue (Cemetery West Side)

Augusta, ME 04330

Cemetery POC(s): Mr. John Spruyt, Massachusetts National Cemetery Director

Phone Number: (508) 563-7113 or by e-mail: John.Spruyt@va.gov

**SECTION B – DESCRIPTION / SPECIFICATION /STATEMENT OF WORK**

 **Project Location:**

**TOGUS NATIONAL CEMETERY (WEST SECTION)**

**Project Title: Repair Mausoleum Wall**

**Project Control #: 818-NRM17-07**

**Statement of Work Summary:**

Contractor shall furnish all tools, labor, materials, equipment, services, and professional design services to perform work described below, in other specification sections, and on the drawings at Togus National Cemetery as required by the project documents.

A. General

1. Contractor is strongly encouraged to survey the project area prior to bidding to adequately understand the full scope of work and all requirements. Contractor is required to submit any questions or clarifications prior to bid. A bid submitted will be taken as agreement that the work shall be performed to meet the requirements herein based on the existing conditions in the field.

2. This numbered requirement only applies to work items specifically noted as DESIGN BUILD ELEMENTS below. The contractor shall engage the services of a professional design firm which specializes in the work contained in this project. Contractor shall submit this firm for approval complete with qualifications prior to the start of construction. Contractor and this professional design firm shall submit design drawings. Design drawings shall be: scaled drawings, Final construction documents, stamped and sealed by a professional engineer in the state where the work is to take place, submitted full size (30x42”) and in electronic format (pdf) to both the Project Engineer and the Cemetery Director.

3. This numbered requirement only applies to work items specifically noted as DESIGN BUILD ELEMENTS below. Where a work item is noted as a DESIGN BUILD ELEMENT a professional engineer’s review shall be performed prior to submission. Prior to submission to the COR, contractor shall have all submittals reviewed, signed and sealed by a professional engineer in the state where work is to take place, and stamped approved by this professional design firm.

4. The contractor shall submit submittals including shop drawings and any other specification requirements to the COR for review and approval prior to fabrication/installation. Submittals approved by the owner (NCA) are required prior to starting on the corresponding work.

B. Specific work items:

1. DESIGN BUILD ELEMENT. Requirements stated herein shall be the minimum requirements. Replace entire historic stone wall, referencing drawings for more information and pictures. New work shall match existing in appearance. Remove all loose existing mortar and stones, save stones for reuse.

Reinstall using new mortar and existing stones, using existing stones as much as possible. No more than 20% of the wall’s stones removed shall be permitted to be replaced using new stones. Any new stones used shall match the existing stones and be submitted for approval. See specification sections for more information on mortaring and testing lab services which shall be required. Use type S mortar for the repairs in this project. Demolish existing reinforced concrete foundation. Design and build a new reinforced concrete foundation hidden from public view below grade.

a. Specific requirements to the existing dry stack stone wall:

Reference drawing 818-NRM17-07-001 detail 3 for delineation and detail 2 for another picture. This existing dry stack wall shall be reinstalled with new type S mortar but only in the back of the wall where not exposed to view. The newly installed wall shall therefore not have visible mortar when viewed from the front. Utilize mortar along the sides of each stone such that sufficient structural strength is provided for this wall to hold back the adjacent earth, but such that the mortar is not visible from the front of the wall.

2. DESIGN BUILD ELEMENT. Reference drawing 818-NRM17-07-001 details 4, 5, 6 & 7. Provide shoring as necessary for the work described in this item. Shoring shall support the existing walls and ceiling and be submitted as a shoring plan, signed and sealed by a professional structural/civil engineer. Tuckpoint the interior walls of the mausoleum by removing the existing mortar where failed, removing existing stones where loose, and then installing new mortar and existing stones. Assume for bidding purposes that 25% of the interior wall area, in small sections spread throughout the four (4) walls, will require rework as described in this work item. New mortar shall be type S. New work shall match existing in appearance. Reinstall using new mortar and existing stones, using existing stones as much as possible. No more than 20% of the wall’s stones removed shall be permitted to be replaced using new stones. Any new stones used shall match the existing stones and be submitted for approval. See specification sections for more information on mortaring and testing lab services which shall be required.

3. Reference drawing 818-NRM17-07-002 details 1, 2 & 3. Demolish existing two (2) prefabricated metal buildings. Install two (2) new prefabricated metal buildings. The existing buildings are to be assumed for bidding purposes as 12’ wide and 15’ long. New buildings shall match size of existing including height of interior space. Verify measurements in field and match size such that the existing foundation can be reused. Reference aforementioned drawing details, and project specifications for more information. Work includes a small amount of concrete foundation repair as shown in detail 3 of the referenced drawing.

4. Reference drawing 818-NRM17-07-002 details 4 & 5. Clean and restore the monument in accordance with the project specifications. Remove existing paint, prepare surfaces, and paint the monument in accordance with the project specifications. The work discussed in this work item shall restore the monument to excellent condition to match existing in color and appearance.

5. Reference drawing 818-NRM17-07-002 detail 6. Secure the loose metal railing into the concrete stair slab using epoxy. Use structural epoxy and install per specification section 033000.

SPECIFICATION SECTIONS:

01 00 02 General Requirements

01 33 23 Shop Drawings, Product Data, and Samples

01 42 19 Reference standards

01 45 29 Testing Lab Services

01 74 19 Construction Waste Management

02 41 10 Demolition and Site Clearing

3 30 00 Cast-In-Place Concrete

04 05 13 Masonry Mortaring

04 05 31 Masonry Truck Pointing

04 20 00 Unit Masonry

05 99 00 Prefabricated Metal Buildings

09 91 00 Painting

31 20 11 Earth Moving (Short Form)

45 10 00 Historic Monument Restoration and Cleaning

DRAWINGS:

818-NRM17-07-001

818-NRM17-07-002

# INFORMATION REGARDING BIDDING MATERIAL, BID GUARANTEE AND BONDS

|  |  |  |
| --- | --- | --- |
| **FAR Number** | **Title** | **Date** |
| 52.228-1 | BID GUARANTEE | SEP 1996 |
| 52.228-2 | ADDITIONAL BOND SECURITY | OCT 1997 |
| 52.228-11 | PLEDGES OF ASSETS | JAN 2012 |
| 52.228-12 | PROSPECTIVE SUBCONTRACTOR REQUESTS FOR BONDS | MAY 2014 |
| 52.228-14 | IRREVOCABLE LETTER OF CREDIT | NOV 2014 |
| 52.228-15 | PERFORMANCE AND PAYMENT BONDS—CONSTRUCTION | OCT 2010 |

## 1.1 52.228-5 INSURANCE—WORK ON A GOVERNMENT INSTALLATION (JAN 1997)

 (a) The Contractor shall, at its own expense, provide and maintain during the entire performance of this contract, at least the kinds and minimum amounts of insurance required in the Schedule or elsewhere in the contract.

 (b) Before commencing work under this contract, the Contractor shall notify the Contracting Officer in writing that the required insurance has been obtained. The policies evidencing required insurance shall contain an endorsement to the effect that any cancellation or any material change adversely affecting the Government's interest shall not be effective—

 (1) For such period as the laws of the State in which this contract is to be performed prescribe; or

 (2) Until 30 days after the insurer or the Contractor gives written notice to the Contracting Officer, whichever period is longer.

 (c) The Contractor shall insert the substance of this clause, including this paragraph (c), in subcontracts under this contract that require work on a Government installation and shall require subcontractors to provide and maintain the insurance required in the Schedule or elsewhere in the contract. The Contractor shall maintain a copy of all subcontractors' proofs of required insurance, and shall make copies available to the Contracting Officer upon request.

(End of Clause)

## 1.2 52.228-13 ALTERNATIVE PAYMENT PROTECTIONS (JULY 2000)

 (a) The Contractor shall submit one of the following payment protections:

 (b) The amount of the payment protection shall be 100 percent of the contract price.

 (c) The submission of the payment protection is required within days of contract award.

 (d) The payment protection shall provide protection for the full contract performance period plus a one-year period.

 (e) Except for escrow agreements and payment bonds, which provide their own protection procedures, the Contracting Officer is authorized to access funds under the payment protection when it has been alleged in writing by a supplier of labor or material that a nonpayment has occurred, and to withhold such funds pending resolution by administrative or judicial proceedings or mutual agreement of the parties.

 (f) When a tripartite escrow agreement is used, the Contractor shall utilize only suppliers of labor and material that signed the escrow agreement.

(End of Clause)

## 1.3 SUPPLEMENTAL INSURANCE REQUIREMENTS

 In accordance with FAR 28.307-2 and FAR 52.228-5, the following minimum coverage shall apply to this contract:

 (a) Workers' compensation and employers liability: Contractors are required to comply with applicable Federal and State workers' compensation and occupational disease statutes. If occupational diseases are not compensable under those statutes, they shall be covered under the employer's liability section of the insurance policy, except when contract operations are so commingled with a Contractor's commercial operations that it would not be practical to require this coverage. Employer's liability coverage of at least $100,000 is required, except in States with exclusive or monopolistic funds that do not permit workers' compensation to be written by private carriers.

 (b) General Liability: $500,000.00 per occurrences.

 (c) Automobile liability: $200,000.00 per person; $500,000.00 per occurrence and $20,000.00 property damage.

 (d) The successful bidder must present to the Contracting Officer, prior to award, evidence of general liability insurance without any exclusionary clauses for asbestos that would void the general liability coverage.

(End of Clause)

#

# INSTRUCTIONS, CONDITIONS AND OTHER STATEMENTS TO BIDDERS/OFFERORS

## 2.1 52.212-1 INSTRUCTIONS TO OFFERORS—COMMERCIAL ITEMS (OCT 2016)

 (a) *North American Industry Classification System (NAICS) code and small business size standard*. The NAICS code and small business size standard for this acquisition appear in Block 10 of the solicitation cover sheet (SF 1449). However, the small business size standard for a concern which submits an offer in its own name, but which proposes to furnish an item which it did not itself manufacture, is 500 employees.

 (b) *Submission of offers*. Submit signed and dated offers to the office specified in this solicitation at or before the exact time specified in this solicitation. Offers may be submitted on the SF 1449, letterhead stationery, or as otherwise specified in the solicitation. As a minimum, offers must show—

 (1) The solicitation number;

 (2) The time specified in the solicitation for receipt of offers;

 (3) The name, address, and telephone number of the offeror;

 (4) A technical description of the items being offered in sufficient detail to evaluate compliance with the requirements in the solicitation. This may include product literature, or other documents, if necessary;

 (5) Terms of any express warranty;

 (6) Price and any discount terms;

 (7) "Remit to" address, if different than mailing address;

 (8) A completed copy of the representations and certifications at FAR 52.212-3 (see FAR 52.212-3(b) for those representations and certifications that the offeror shall complete electronically);

 (9) Acknowledgment of Solicitation Amendments;

 (10) Past performance information, when included as an evaluation factor, to include recent and relevant contracts for the same or similar items and other references (including contract numbers, points of contact with telephone numbers and other relevant information); and

 (11) If the offer is not submitted on the SF 1449, include a statement specifying the extent of agreement with all terms, conditions, and provisions included in the solicitation. Offers that fail to furnish required representations or information, or reject the terms and conditions of the solicitation may be excluded from consideration.

 (c) *Period for acceptance of offers*. The offeror agrees to hold the prices in its offer firm for 30 calendar days from the date specified for receipt of offers, unless another time period is specified in an addendum to the solicitation.

 (d) *Product samples*. When required by the solicitation, product samples shall be submitted at or prior to the time specified for receipt of offers. Unless otherwise specified in this solicitation, these samples shall be submitted at no expense to the Government, and returned at the sender's request and expense, unless they are destroyed during preaward testing.

 (e) *Multiple offers*. Offerors are encouraged to submit multiple offers presenting alternative terms and conditions or commercial items for satisfying the requirements of this solicitation. Each offer submitted will be evaluated separately.

 (f) Late submissions, modifications, revisions, and withdrawals of offers.

 (1) Offerors are responsible for submitting offers, and any modifications, revisions, or withdrawals, so as to reach the Government office designated in the solicitation by the time specified in the solicitation. If no time is specified in the solicitation, the time for receipt is 4:30 p.m., local time, for the designated Government office on the date that offers or revisions are due.

 (2)(i) Any offer, modification, revision, or withdrawal of an offer received at the Government office designated in the solicitation after the exact time specified for receipt of offers is "late" and will not be considered unless it is received before award is made, the Contracting Officer determines that accepting the late offer would not unduly delay the acquisition; and—

 (A) If it was transmitted through an electronic commerce method authorized by the solicitation, it was received at the initial point of entry to the Government infrastructure not later than 5:00 p.m. one working day prior to the date specified for receipt of offers; or

 (B) There is acceptable evidence to establish that it was received at the Government installation designated for receipt of offers and was under the Government's control prior to the time set for receipt of offers; or

 (C) If this solicitation is a request for proposals, it was the only proposal received.

 (ii) However, a late modification of an otherwise successful offer, that makes its terms more favorable to the Government, will be considered at any time it is received and may be accepted.

 (3) Acceptable evidence to establish the time of receipt at the Government installation includes the time/date stamp of that installation on the offer wrapper, other documentary evidence of receipt maintained by the installation, or oral testimony or statements of Government personnel.

 (4) If an emergency or unanticipated event interrupts normal Government processes so that offers cannot be received at the Government office designated for receipt of offers by the exact time specified in the solicitation, and urgent Government requirements preclude amendment of the solicitation or other notice of an extension of the closing date, the time specified for receipt of offers will be deemed to be extended to the same time of day specified in the solicitation on the first work day on which normal Government processes resume.

 (5) Offers may be withdrawn by written notice received at any time before the exact time set for receipt of offers. Oral offers in response to oral solicitations may be withdrawn orally. If the solicitation authorizes facsimile offers, offers may be withdrawn via facsimile received at any time before the exact time set for receipt of offers, subject to the conditions specified in the solicitation concerning facsimile offers. An offer may be withdrawn in person by an offeror or its authorized representative if, before the exact time set for receipt of offers, the identity of the person requesting withdrawal is established and the person signs a receipt for the offer.

 (g) *Contract award (not applicable to Invitation for Bids).* The Government intends to evaluate offers and award a contract without discussions with offerors. Therefore, the offeror's initial offer should contain the offeror's best terms from a price and technical standpoint. However, the Government reserves the right to conduct discussions if later determined by the Contracting Officer to be necessary. The Government may reject any or all offers if such action is in the public interest; accept other than the lowest offer; and waive informalities and minor irregularities in offers received.

 (h) *Multiple awards.* The Government may accept any item or group of items of an offer, unless the offeror qualifies the offer by specific limitations. Unless otherwise provided in the Schedule, offers may not be submitted for quantities less than those specified. The Government reserves the right to make an award on any item for a quantity less than the quantity offered, at the unit prices offered, unless the offeror specifies otherwise in the offer.

 (i) Availability of requirements documents cited in the solicitation.

 (1)(i) The GSA Index of Federal Specifications, Standards and Commercial Item Descriptions, FPMR Part 101-29, and copies of specifications, standards, and commercial item descriptions cited in this solicitation may be obtained for a fee by submitting a request to—

GSA Federal Supply Service Specifications Section

Suite 8100 470 East L'Enfant Plaza, SW

Washington, DC 20407

Telephone (202) 619-8925

Facsimile (202) 619-8978.

 (ii) If the General Services Administration, Department of Agriculture, or Department of Veterans Affairs issued this solicitation, a single copy of specifications, standards, and commercial item descriptions cited in this solicitation may be obtained free of charge by submitting a request to the addressee in paragraph (i)(1)(i) of this provision. Additional copies will be issued for a fee.

 (2) Most unclassified Defense specifications and standards may be downloaded from the following ASSIST websites:

 (i) ASSIST (<https://assist.dla.mil/online/start/>);

 (ii) Quick Search (<http://quicksearch.dla.mil/>);

 (iii) ASSISTdocs.com (<http://assistdocs.com>).

 (3) Documents not available from ASSIST may be ordered from the Department of Defense Single Stock Point (DoDSSP) by?

 (i) Using the ASSIST Shopping Wizard (<https://assist.dla.mil/wizard/index.cfm>);

 (ii) Phoning the DoDSSP Customer Service Desk (215) 697-2179, Mon-Fri, 0730 to 1600 EST; or

 (iii) Ordering from DoDSSP, Building 4, Section D, 700 Robbins Avenue, Philadelphia, PA 19111-5094, Telephone (215) 697-2667/2179, Facsimile (215) 697-1462.

 (4) Nongovernment (voluntary) standards must be obtained from the organization responsible for their preparation, publication, or maintenance.

 (j) *Unique entity identifier*. (Applies to all offers exceeding $3,500, and offers of $3,500 or less if the solicitation requires the Contractor to be registered in the System for Award Management (SAM) database.) The Offeror shall enter, in the block with its name and address on the cover page of its offer, the annotation ‘‘Unique Entity Identifier’’ followed by the unique entity identifier that identifies the Offeror’s name and address. The Offeror also shall enter its Electronic Funds Transfer (EFT) indicator, if applicable. The EFT indicator is a four-character suffix to the unique entity identifier. The suffix is assigned at the discretion of the Offeror to establish additional SAM records for identifying alternative EFT accounts (see subpart 32.11) for the same entity. If the Offeror does not have a unique entity identifier, it should contact the entity designated at [www.sam.gov](file:///C%3A%5CUsers%5CcemDukesH%5CAppData%5CLocal%5CMicrosoft%5CWindows%5CTemporary%20Internet%20Files%5CContent.Outlook%5CGO74GZ8V%5Cwww.sam.gov) for unique entity identifier establishment directly to obtain one. The Offeror should indicate that it is an offeror for a Government contract when contacting the entity designated at [www.sam.gov](file:///C%3A%5CUsers%5CcemDukesH%5CAppData%5CLocal%5CMicrosoft%5CWindows%5CTemporary%20Internet%20Files%5CContent.Outlook%5CGO74GZ8V%5Cwww.sam.gov) for establishing the unique entity identifier.

 (k) *System for Award Management*. Unless exempted by an addendum to this solicitation, by submission of an offer, the offeror acknowledges the requirement that a prospective awardee shall be registered in the SAM database prior to award, during performance and through final payment of any contract resulting from this solicitation. If the Offeror does not become registered in the SAM database in the time prescribed by the Contracting Officer, the Contracting Officer will proceed to award to the next otherwise successful registered Offeror. Offerors may obtain information on registration and annual confirmation requirements via the SAM database accessed through <https://www.acquisition.gov>.

 (l) *Debriefing*. If a post-award debriefing is given to requesting offerors, the Government shall disclose the following information, if applicable:

 (1) The agency's evaluation of the significant weak or deficient factors in the debriefed offeror's offer.

 (2) The overall evaluated cost or price and technical rating of the successful and the debriefed offeror and past performance information on the debriefed offeror.

 (3) The overall ranking of all offerors, when any ranking was developed by the agency during source selection.

 (4) A summary of the rationale for award;

 (5) For acquisitions of commercial items, the make and model of the item to be delivered by the successful offeror.

 (6) Reasonable responses to relevant questions posed by the debriefed offeror as to whether source-selection procedures set forth in the solicitation, applicable regulations, and other applicable authorities were followed by the agency.

(End of Provision)

ADDENDUM to FAR 52.212-1 INSTRUCTIONS TO OFFERORS—COMMERCIAL ITEMS

**52.219-6 Notice of Total Small Business Set-Aside.**

As prescribed in [19.508](https://www.acquisition.gov/sites/default/files/current/far/html/Subpart%2019_5.html#wp1086899)(c), insert the following clause:

Notice of Total Small Business Set-Aside (Nov 2011)

(a) Definition. “Small business concern,” as used in this clause, means a concern, including its affiliates, that is independently owned and operated, not dominant in the field of operation in which it is bidding on Government contracts, and qualified as a small business under the size standards in this solicitation.

(b) Applicability. This clause applies only to—

(1) Contracts that have been totally set aside or reserved for small business concerns; and

(2) Orders set aside for small business concerns under multiple-award contracts as described in 8.405-5 and 16.505(b)(2)(i)(F).

(c) General.

(1) Offers are solicited only from small business concerns. Offers received from concerns that are not small business concerns shall be considered nonresponsive and will be rejected.

(2) Any award resulting from this solicitation will be made to a small business concern.

(d) Agreement. A small business concern submitting an offer in its own name shall furnish, in performing the contract, only end items manufactured or produced by small business concerns in the United States or its outlying areas. If this procurement is processed under simplified acquisition procedures and the total amount of this contract does not exceed $25,000, a small business concern may furnish the product of any domestic firm. This paragraph does not apply to construction or service contracts.

**SUBMITTAL OF QUOTES / PROPOSALS:**

1. All proposals must be submitted through the Department of Veterans Affairs - Electronic Management System (eCMS) Vendor Portal website in order to be considered for award. <https://www.vendorportal.ecms.va.gov>
2. Please go to the VA eCMS Vendor Portal website at <https://www.vendorportal.ecms.va.gov> to register. Once on the webpage, proceed to the Vendor Portal Login section located on the far left side of the webpage and click on ‘Request a user account’ to register. In the event an Offeror is unable to submit a proposal through the Vendor Portal domain, prior to the proposal closing date, contact the VAAS helpdesk at 1-877-634-3739, or via email at VA.Acquisition.Systems@va.gov. Submission of proposals through email will not be accepted. Proposal transmission/uploads must be completed by the date/time specified. Late or incomplete Proposals will not be considered.
3. If Offerors are still unable to submit a proposal through VA eCMS Vendor Portal, the Offerors may submit a CD version of their proposal package as long as VA eCMS Vendor Portal registration requirements have been fulfilled and Offerors have contacted the VAAS helpdesk for assistance in their submission of a proposal. A copy of the email correspondence with the VAAS helpdesk will be forwarded to the Contracting Officer, Henry Dukes at henry.dukes@va.gov as proof of email correspondence. If a phone conversation with the VAAS helpdesk proves unsuccessful in an Offeror’s ability to submit a proposal prior to the closing date via Vendor Portal, the Offeror shall submit to the Contracting Officer correspondence that contains the date, time, and name of helpdesk representative the Offeror contacted to include the reasons why the Offeror could not submit a proposal via the Portal. This document will be submitted together with the CD version of the proposal. **In the event an Offeror has not requested proposal submission assistance to the VAAS help desk prior to the closing date, nor has submitted correspondence that identifies reasons why the Offeror could not submit a proposal via Vendor Portal, the Offeror will be considered non responsive and the CD version of the proposal will not be accepted.**
4. If a CD version of the proposal is accepted by the Contracting Officer, the CD version of the proposal may be submitted as an MS Word document. If PDF is preferred, then each Section submitted shall be a separate file. For example, all required licenses, technical proposal, Past Performance Questionnaires, shall all be under separate files and shall be classified as such. The CD shall be categorized in a manner where it is easy to ascertain. Offers who meet stated requirements may submit a CD version of their proposals at the address specified in Block 9 of SF 1449, or if hand carried, to the address shown in block 9, until the date and time specified in Block 8. CAUTION - LATE Submissions, Modifications, and Withdrawals: See provision 52.212-1. All offers are subject to all terms and conditions of this solicitation. Offers authorized to submit CD versions of their proposals are to submit their proposals to the Contracting Officer's Office, i.e., the Issuing Office address that appears in Block 9 of the SF-1449 above.

**PROPOSAL PACKAGE**

1. Price Schedule
2. Technical Qualifications in a written narrative for the Government’s evaluation.
3. Three (3) Past Performance references within the last five (5) years that are similar in size and scope to this solicitation. Use the Past Performance Questionnaire. Prepare one for each reference. Additional references will not be acknowledged. Only the (3) most current past performances will be reviewed.
4. Required representations and certifications.
5. Acknowledgement of any amendments.

**Failure to submit all required documentation may result in your submission being determined technically unacceptable and removed from further consideration.**

**PROPOSAL FORMAT**

1. Page size shall be no greater than 8 1/2" x 11". The top, bottom, left, and right margins shall be a minimum of one (1) inch each.
2. Font size shall be no smaller than 11-point. Arial or Times New Roman fonts are required. Characters shall be set at no less than normal spacing and 100% scale.
3. Tables and illustrations may use a reduced font size no smaller than eight (8)-point and may be landscape.
4. Line spacing shall be set at no less than single space.
5. Each paragraph shall be separated by at least one blank line.
6. Page numbers, company logos, and headers and footers may be within the page margins only and are not bound by the 11-point font requirement.
7. Footnotes to text shall not be added.
8. If the Offeror submits annexes, documentation, attachments or the like, not specifically required by this solicitation, such will count against the offeror’s page limitations unless otherwise indicated in the specific volume instructions below.
9. Pages in violation of these instructions, either by exceeding the margin, font, or spacing restrictions or by exceeding the total page limit for a particular volume, **will not be** evaluated.
10. The following page limitations are applicable to this procurement:

|  |  |  |
| --- | --- | --- |
| **Volume**  | **Factor** | **Page Limitations** |
| Volume I | Technical | 20 pages single-sided |
| Volume II | Past Performance | 6 pages single-sided |
| Volume III | Price | No Limit |

**A cover page and/or table of contents which are not required will be included in the page count of the Technical Volume if included in the Volume.**

**A glossary of abbreviations or acronyms will not be included in the page count of the Technical Volume.**

**Proposal packages that do not contain all the above materials may be rejected.**

**Proposal packages that fail to include sufficient Technical, Past Performance and/or Price information for a competitive evaluation may result in the proposal being rejected and not considered.**

**Proposals that are not received completely by the time and date specified in Block 8 of the SF 1449 will be rejected and shall not be considered.**

Provisions that are incorporated by reference (by Citation Number, Title, and Date), have the same force and effect as if they were given in full text. Upon request, the Contracting Officer will make their full text available.

 The following provisions are incorporated into 52.212-1 as an addendum to this solicitation:

 The following provisions are incorporated into 52.212-1 as an addendum to this solicitation:

 (End of Addendum to 52.212-1)

## 2.2 52.212-2 EVALUATION—COMMERCIAL ITEMS (OCT 2014)

This procurement will be Small Business Set Aside using a Cascading Set-Aside Procedure. The Government will award at the highest possible tier. **The tiers will be as follows:**

**1st tier- SDVOSB**

**2nd tier- VOSB**

**3rd tier- All Other Small Businesses**

**SOURCE SELECTION PROCESS - LOWEST PRICE TECHNICALLY ACCEPTABLE USING A CASCADING SET-ASIDE PROCEDURE**

**METHOD OF AWARD – CASCADE PROCEDURES**

This a competitive Request for Proposals (RFP) using a Three (3)-Tier cascading set-aside procedure. The set-aside requirement will be as follows: First (1st) Tier: Service Disabled Veteran Owned Small Businesses (SDVOSB), Second (2nd) Tier: Veteran Owned Small Businesses, Third (3rd) Tier: All Other Small Businesses. Cascading process will be used in conjunction with FAR Part 15, Lowest Price Technically Acceptable (LPTA) source selection process.

Award will be made to a responsible offeror on the basis of the lowest evaluated price of proposals meeting or exceeding the acceptability standards for non-cost factors; only were adequate/sufficient competition is received at a given tier.

Adequate competition exists if; (1) proposals are received from at least two responsible offerors; (2) each of whom can satisfy the contract's requirements independently; (3) both contend for a contract which will be won by the offeror who submits the lowest evaluated price meeting or exceeding technical requirement and; (4) price is reasonable.

If adequate competition is met as described above and also meets the requirement in price reasonableness - award procedure will be initiated. If adequate competition is not met, or prices are not reasonable, competition will proceed at the next lower tier. The process through the tiers will be executed as needed.

The Government will award a Firm-Fixed Price contract resulting from this solicitation to the responsible offeror whose proposal is the lowest evaluate price of proposals meeting or exceeding the acceptability standards for non-cost factors. The award will be made without discussion. Therefore, the offeror’s initial proposal should contain optimal terms from a price and technical standpoint.

The following factors listed in descending order of importance will be used to evaluate offers: (1) Price, (2) Past Performance; and (3) Technical Capability. Past Performance and Technical Capability when combined are not more important than Price.

1. Options: Option years are not applicable to this requirement.
2. A written notice of award or acceptance of an offer mailed or otherwise furnished to the successful offeror within the time for acceptance specified in the offer shall result in a binding contract without further actions to be taken by either party.

**EVALUATION OF QUOTATIONS:**

Proposals will be evaluated based on the following factors listed as shown below:

**PRICE:**

Price will be evaluated for reasonableness and realism **i**n order to ensure a fair and reasonable price. The Government will compare proposed prices received in response to the solicitation. Normally, adequate price competition establishes a fair and reasonable price when two or more responsible offerors, competing independently, submit priced offers that satisfy the Government’s expressed requirement.

In addition to a price comparison, proposed prices will also be compared to the Independent Government Estimate. A proposal that provides a price with no substantial information on pricing and/or performance will result in an inferior proposal and maybe considered non-responsive. In limited situations, a cost analysis may be appropriate to establish reasonableness of the otherwise successful offeror’s price. In addition, offerors are cautioned against submitting an offer that contains unbalanced pricing. Unbalanced pricing exits when, despite an acceptable total evaluated price, the price of one or more contract line items for the base and or option years is significantly overstated or understated as indicated by the application of analysis techniques. Offers that are determined to be unbalanced may be rejected if the lack of balance poses an unacceptable risk to the Government.

The Government will not consider offers that are considerably low or too high. Pricing may be compared against the IGCE or against the average mean of the offers received to arrive at a competitive range in determining too low/too high offers. Also, if a wage rate is included with this solicitation, provide the proposed wages you will be paying to compare against the wage rate. You can provide this as a range if you do not want to list direct wages. Wage rates only apply to hourly employees, not salary employees; but you cannot convert a traditionally hourly employee to a salary employee to avoid the wage rate.

**PAST PERFORMANCE:** Past Performance will be evaluated for quality, timeliness (e.g. recent), problem resolution, business relations, customer service and relevance (e.g. experience in providing services similar in size, scope, and complexity as described in the SOW). If no past performance information is readily available, the offeror’s past performance will be evaluated as Neutral. The Government will research information and data bases to aid in establishing the contractor’s responsibility and ability to perform the required services. The databases include but are not limited to Experian, CPARS, EPLS, VetBiz, and SBA. In addition, please provide a list with a minimum of three (3) contracts and/or subcontracts that have been held over the past five (5) years providing services similar in size, scope, and complexity. Any additional information such as letters, associations, and standards to substantiate the past performance shall be furnished by the offeror. The offeror shall provide the following information for each contract and/or subcontract:

1. Customer’s name, address, telephone numbers of customers lead contact and technical personnel
2. Contract Number
3. Contract Dollar Value
4. Any terminations (partial or complete) and the reason (convenience or default)

**TECHNICAL CAPABILITY:** Technical capability will be evaluated to determine the extent to which contractors demonstrate a clear understanding of all features involved in the performance of the requirements identified in the Statement of Work. The proposal should not simply restate the Government’s requirements, but it should describe, in detail, how the offeror intends to meet the requirements. In particular, offerors must provide information for the following sub-factors, which are weighted equally:

**Sub-Factor 1 – Corporate Project Experience:**

The offeror shall provide information on your company’s capabilities; years in business; type and age of equipment to be used on the project; demonstrate corporate experience with no more than three (3) projects completed within the last five (5) years and/or similar in size and scope to this project as outlined in the solicitation specifically addressing projects you have completed that are similar to this request. In describing project experience, provide the following:

1. Project title, location, and a brief description
2. Project owner, name, telephone number of owner’s contact person
3. Project’s Prime contractor and major sub-contractors and name and telephone number of each contact person(s). NOTE: Each firm and managing person(s) (project manager/superintendent/foreman as the case may be) proposed for this project
4. Project start and completion dates (original vs. actual), reasons for any delays and/or change orders
5. Experience in the proposed area industry market
6. List number of projects currently ongoing and of that number the number that may affect this proposal and there completion date(s). NOTE: location of head office, branch office(s) and location of person with authority to sign contractual documents.

. **Sub-Factor 2 – Project Personnel Experience:**

The offeror shall demonstrate the specialized experience and technical competence of the key personnel who will be assigned to this project specifically addressing projects with an emphasis on working within a National Cemetery or similar location/venue. At a minimum, this shall include both the Project Manager and on-site superintendent/foreman. In describing this criteria, provide the following:

1. Name of individual
2. Firm employed by and/or with
3. Company position and title
4. Years with the company
5. Describe work experience with project(s) similar in scope
6. Indication of which, if any, project(s) submitted under Corporate experience above, the individual participated in and what the individuals responsibility while assigned to the project(s)
7. Position and/or responsibility that individual will hold in regards to the project team, description of duties and what percentage of the individual’s time will be committed to this project. Describe educational background/experience, including degrees, certifications, etc. and granting institution
8. Experience of local market/conditions of key personnel assigned to the project

**Sub-Factor 3 – Technical/Management Approach:**

The offeror shall demonstrate the following relevant to the subject project:

1. Project Delivery Philosophy including statements of commitment and conflict resolution
2. Offerors’ Quality Assurance and Quality Control Programs/measurements
3. Capability to perform, including offeror’s total bonding capacity, current available bonding capacity and projected available bonding capacity

**Sub-Factor 4 – Scheduling/Phasing:**

The offeror shall demonstrate the following:

1. Approach for this project, including a proposed project work schedule in a time scaled bar graph format beginning with the Notice to Proceed and concluding with contract completion. All schedule items shall show, start date and completion date, specific tasks, labor man hours and cost for each schedule item with allotted time for weather, interments, and government holidays
2. Provide a written narrative plan to demonstrate understanding of the safety and phasing requirements to include documentation of site-supervisor and/or foreman completion of 10 hour OSHA training
3. List subcontractors - their social economic status (i.e. Disabled Veteran, Veteran, Small, Large Business, etc.) - and percent of work they will perform; (iv) the surveyor/survey company you will be using

**Sub-Factor 5 – Registered in the System for Award Management (SAM):**

1. Offeror shall provide a valid SAM Registration Report showing an active/current registration date.

**Sub-Factor 6 – Registered in the Vendor Information Pages (VIP) and the Verification Case Management System (VCMS) via** [**www.vip.vetbiz.gov**](http://www.vip.vetbiz.gov)**:**

Offeror shall provide a valid Service Disabled Veteran Owned Small Business (SDVOSB) active registration certificate.

**Failure to submit all required documentation as required may result in your submission being found to be technically unacceptable.**

(End of Provision)

## 2.3 LIMITATIONS ON SUBCONTRACTING--MONITORING AND COMPLIANCE (JUN 2011)

 This solicitation includes VAAR 852.219-10 VA Notice of Total Service- Disabled Veteran-Owned Small Business Set-Aside. Accordingly, any contract resulting from this solicitation will include this clause. The contractor is advised in performing contract administration functions, the CO may use the services of a support contractor(s) retained by VA to assist inassessing the contractor's compliance with the limitations on subcontracting or percentage of work performance requirements specified in the clause. To that end, the support contractor(s) may require access to contractor's offices where the contractor's business records or other proprietary data are retained and to review such business records regarding the contractor's compliance with this requirement. All support contractors conducting this review on behalf of VA will be required to sign an “Information Protection and Non-Disclosure and Disclosure of Conflicts of Interest Agreement” to ensure the contractor's business records or other proprietary data reviewed or obtained in the course of assisting the CO in assessing the contractor for compliance are protected to ensure information or data is not improperly disclosed or other impropriety occurs. Furthermore, if VA determines any services the support contractor(s) will perform in assessing compliance are advisory and assistance services as defined in FAR 2.101, Definitions, the support contractor(s) must also enter into an agreement with the contractor to protect proprietary information as required by FAR 9.505-4, obtaining access to proprietary information, paragraph (b). The contractor is required to cooperate fully and make available any records as may be required to enable the CO to assess the contractor's compliance with the limitations on subcontracting or percentage of work performance requirement.

## 2.4 52.252-1 SOLICITATION PROVISIONS INCORPORATED BY REFERENCE (FEB 1998)

 This solicitation incorporates one or more solicitation provisions by reference, with the same force and effect as if they were given in full text. Upon request, the Contracting Officer will make their full text available. The offeror is cautioned that the listed provisions may include blocks that must be completed by the offeror and submitted with its quotation or offer. In lieu of submitting the full text of those provisions, the offeror may identify the provision by paragraph identifier and provide the appropriate information with its quotation or offer. Also, the full text of a solicitation provision may be accessed electronically at this/these address(es):

 http://www.acquisition.gov/far/index.html

 http://www.va.gov/oal/library/vaar/

(End of Provision)

|  |  |  |
| --- | --- | --- |
| **FAR Number** | **Title** | **Date** |
| 52.204-6 | UNIQUE ENTITY IDENTIFIER | OCT 2016 |
| 52.204-7 | SYSTEM FOR AWARD MANAGEMENT | OCT 2016 |
| 52.204-16 | COMMERCIAL AND GOVERNMENT ENTITY CODE REPORTING | JUL 2016 |
| 52.204-17 | OWNERSHIP OR CONTROL OF OFFEROR | JUL 2016 |
| 52.214-34 | SUBMISSION OF OFFERS IN THE ENGLISH LANGUAGE | APR 1991 |
| 52.214-35 | SUBMISSION OF OFFERS IN U.S. CURRENCY | APR 1991 |
| 52.232-38 | SUBMISSION OF ELECTRONIC FUNDS TRANSFER INFORMATION WITH OFFER | JUL 2013 |
| 52.236-28 | PREPARATION OF PROPOSALS—CONSTRUCTION | OCT 1997 |

## 2.5 52.209-7 INFORMATION REGARDING RESPONSIBILITY MATTERS (JUL 2013)

 (a) *Definitions.* As used in this provision—

 "Administrative proceeding" means a non-judicial process that is adjudicatory in nature in order to make a determination of fault or liability (e.g., Securities and Exchange Commission Administrative Proceedings, Civilian Board of Contract Appeals Proceedings, and Armed Services Board of Contract Appeals Proceedings). This includes administrative proceedings at the Federal and State level but only in connection with performance of a Federal contract or grant. It does not include agency actions such as contract audits, site visits, corrective plans, or inspection of deliverables.

 "Federal contracts and grants with total value greater than $10,000,000" means—

 (1) The total value of all current, active contracts and grants, including all priced options; and

 (2) The total value of all current, active orders including all priced options under indefinite-delivery, indefinite-quantity, 8(a), or requirements contracts (including task and delivery and multiple-award Schedules).

 "Principal" means an officer, director, owner, partner, or a person having primary management or supervisory responsibilities within a business entity (e.g., general manager; plant manager; head of a division or business segment; and similar positions).

 (b) The offeror [ ] has [ ] does not have current active Federal contracts and grants with total value greater than $10,000,000.

 (c) If the offeror checked "has" in paragraph (b) of this provision, the offeror represents, by submission of this offer, that the information it has entered in the Federal Awardee Performance and Integrity Information System (FAPIIS) is current, accurate, and complete as of the date of submission of this offer with regard to the following information:

 (1) Whether the offeror, and/or any of its principals, has or has not, within the last five years, in connection with the award to or performance by the offeror of a Federal contract or grant, been the subject of a proceeding, at the Federal or State level that resulted in any of the following dispositions:

 (i) In a criminal proceeding, a conviction.

 (ii) In a civil proceeding, a finding of fault and liability that results in the payment of a monetary fine, penalty, reimbursement, restitution, or damages of $5,000 or more.

 (iii) In an administrative proceeding, a finding of fault and liability that results in—

 (A) The payment of a monetary fine or penalty of $5,000 or more; or

 (B) The payment of a reimbursement, restitution, or damages in excess of $100,000.

 (iv) In a criminal, civil, or administrative proceeding, a disposition of the matter by consent or compromise with an acknowledgment of fault by the Contractor if the proceeding could have led to any of the outcomes specified in paragraphs (c)(1)(i), (c)(1)(ii), or (c)(1)(iii) of this provision.

 (2) If the offeror has been involved in the last five years in any of the occurrences listed in (c)(1) of this provision, whether the offeror has provided the requested information with regard to each occurrence.

 (d) The offeror shall post the information in paragraphs (c)(1)(i) through (c)(1)(iv) of this provision in FAPIIS as required through maintaining an active registration in the System for Award Management database via [https://www.acquisition.gov](https://www.acquisition.gov/) (see 52.204-7).

(End of Provision)

## 2.6 52.216-1 TYPE OF CONTRACT (APR 1984)

 The Government contemplates award of a Firm-Fixed-Price contract resulting from this solicitation.

(End of Provision)

## 2.7 52.222-5 CONSTRUCTION WAGE RATE REQUIREMENTS—SECONDARY SITE OF THE WORK (MAY 2014)

 (a)(1) The offeror shall notify the Government if the offeror intends to perform work at any secondary site of the work, as defined in paragraph (a)(1)(ii) of the FAR clause at 52.222-6, Construction Wage Rate Requirements, of this solicitation.

 (2) If the offeror is unsure if a planned work site satisfies the criteria for a secondary site of the work, the offeror shall request a determination from the Contracting Officer.

 (b)(1) If the wage determination provided by the Government for work at the primary site of the work is not applicable to the secondary site of the work, the offeror shall request a wage determination from the Contracting Officer.

 (2) The due date for receipt of offers will not be extended as a result of an offeror's request for a wage determination for a secondary site of the work.

(End of Provision)

## 2.8 52.222-23 NOTICE OF REQUIREMENT FOR AFFIRMATIVE ACTION TO ENSURE EQUAL EMPLOYMENT OPPORTUNITY FOR CONSTRUCTION (FEB 1999)

 (a) The offeror's attention is called to the Equal Opportunity clause and the Affirmative Action Compliance Requirements for Construction clause of this solicitation.

 (b) The goals for minority and female participation, expressed in percentage terms for the Contractor's aggregate workforce in each trade on all construction work in the covered area, are as follows:

|  |  |
| --- | --- |
| **Goals for minority participation for each trade** | **Goals for female participation for each trade** |
| 45.9 % | 6.9 % |

 These goals are applicable to all the Contractor's construction work performed in the covered area. If the Contractor performs construction work in a geographical area located outside of the covered area, the Contractor shall apply the goals established for the geographical area where the work is actually performed. Goals are published periodically in the Federal Register in notice form, and these notices may be obtained from any Office of Federal Contract Compliance Programs office.

 (c) The Contractor's compliance with Executive Order 11246, as amended, and the regulations in 41 CFR 60-4 shall be based on (1) its implementation of the Equal Opportunity clause, (2) specific affirmative action obligations required by the clause entitled "Affirmative Action Compliance Requirements for Construction," and (3) its efforts to meet the goals. The hours of minority and female employment and training must be substantially uniform throughout the length of the contract, and in each trade. The Contractor shall make a good faith effort to employ minorities and women evenly on each of its projects. The transfer of minority or female employees or trainees from Contractor to Contractor, or from project to project, for the sole purpose of meeting the Contractor's goals shall be a violation of the contract, Executive Order 11246, as amended, and the regulations in 41 CFR 60-4. Compliance with the goals will be measured against the total work hours performed.

 (d) The Contractor shall provide written notification to the Deputy Assistant Secretary for Federal Contract Compliance, U.S. Department of Labor, within 10 working days following award of any construction subcontract in excess of $10,000 at any tier for construction work under the contract resulting from this solicitation. The notification shall list the—

 (1) Name, address, and telephone number of the subcontractor;

 (2) Employer's identification number of the subcontractor;

 (3) Estimated dollar amount of the subcontract;

 (4) Estimated starting and completion dates of the subcontract; and

 (5) Geographical area in which the subcontract is to be performed.

 (e) As used in this Notice, and in any contract resulting from this solicitation, the "covered area" is

160 Albuquerque, NM: Non-SMSA-Counties

NM Citron. NM Colfax; NM De Baca; NM Guadalupe; NM San Juan;

NM San Miguel; NM Santa Fe; NM Soco

(End of Provision)

## 2.9 52.225-10 NOTICE OF BUY AMERICAN REQUIREMENT—CONSTRUCTION MATERIALS (MAY 2014)

 (a) *Definitions.* "Commercially available off-the-shelf (COTS) item," "construction material," "domestic construction material," and "foreign construction material," as used in this provision, are defined in the clause of this solicitation entitled "Buy American—Construction Materials" (Federal Acquisition Regulation (FAR) clause 52.225-9).

 (b) *Requests for determinations of inapplicability.* An offeror requesting a determination regarding the inapplicability of the Buy American statute should submit the request to the Contracting Officer in time to allow a determination before submission of offers. The offeror shall include the information and applicable supporting data required by paragraphs (c) and (d) of the clause at FAR 52.225-9 in the request. If an offeror has not requested a determination regarding the inapplicability of the Buy American statute before submitting its offer, or has not received a response to a previous request, the offeror shall include the information and supporting data in the offer.

 (c) Evaluation of offers.

 (1) The Government will evaluate an offer requesting exception to the requirements of the Buy American statute, based on claimed unreasonable cost of domestic construction material, by adding to the offered price the appropriate percentage of the cost of such foreign construction material, as specified in paragraph (b)(3)(i) of the clause at FAR 52.225-9.

 (2) If evaluation results in a tie between an offeror that requested the substitution of foreign construction material based on unreasonable cost and an offeror that did not request an exception, the Contracting Officer will award to the offeror that did not request an exception based on unreasonable cost.

 (d) Alternate offers.

 (1) When an offer includes foreign solicitation in paragraph (b)(2) of the clause at FAR 52.225-9, the offeror also may submit an alternate offer based on use of equivalent domestic construction material.

 (2) If an alternate offer is submitted, the offeror shall submit a separate Standard Form 1442 for the alternate offer, and a separate price comparison table prepared in accordance with paragraphs (c) and (d) of the clause at FAR 52.225-9 for the offer that is based on the use of any foreign construction material for which the Government has not yet determined an exception applies.

 (3) If the Government determines that a particular exception requested in accordance with paragraph (c) of the clause at FAR 52.225-9 does not apply, the Government will evaluate only those offers based on use of the equivalent domestic construction material, and the offeror shall be required to furnish such domestic construction material. An offer based on use of the foreign construction material for which an exception was requested—

 (i) Will be rejected as nonresponsive if this acquisition is conducted by sealed bidding; or

 (ii) May be accepted if revised during negotiations.

(End of Provision)

## 2.10 52.233-2 SERVICE OF PROTEST (SEP 2006)

 Protests, as defined in section 33.101 of the Federal Acquisition Regulation, that are filed directly with an agency, and copies of any protests that are filed with the Government Accountability Office (GAO), shall be served on the Contracting Officer (addressed as follows) by obtaining written and dated acknowledgment of receipt from:

 Henry Dukes

 Contracting Officer, NCA

 Hand-Carried Address:

 Department of Veterans Affairs

 NCA Contracting Service

 75 Barrett Heights Rd. Suite 309

 Stafford VA 22556

 Mailing Address:

 Department of Veterans Affairs

 NCA Contracting Service

 75 Barrett Heights Rd. Suite 309

 Stafford VA 22556

 (b) The copy of any protest shall be received in the office designated above within one day of filing a protest with the GAO.

(End of Provision)

## 2.11 VAAR 852.252-70 SOLICITATION PROVISIONS OR CLAUSES INCORPORATED BY REFERENCE (JAN 2008)

 The following provisions or clauses incorporated by reference in this solicitation must be completed by the offeror or prospective contractor and submitted with the quotation or offer. Copies of these provisions or clauses are available on the Internet at the Web sites provided in the provision at FAR 52.252-1, Solicitation Provisions Incorporated by Reference, or the clause at FAR 52.252-2, Clauses Incorporated by Reference. Copies may also be obtained from the contracting officer.

[Contracting officer shall list all FAR and 48 CFR Chapter 8 (VAAR) provisions and clauses incorporated by reference that must be completed by the offeror or prospective contractor and submitted with the quotation or offer.]

(End of Provision)

|  |  |  |
| --- | --- | --- |
| **FAR Number** | **Title** | **Date** |
| 852.270-1 | REPRESENTATIVES OF CONTRACTING OFFICERS | JAN 2008 |

## 2.12 VAAR 852.233-70 PROTEST CONTENT/ALTERNATIVE DISPUTE RESOLUTION (JAN 2008)

 (a) Any protest filed by an interested party shall:

 (1) Include the name, address, fax number, and telephone number of the protester;

 (2) Identify the solicitation and/or contract number;

 (3) Include an original signed by the protester or the protester's representative and at least one copy;

 (4) Set forth a detailed statement of the legal and factual grounds of the protest, including a description of resulting prejudice to the protester, and provide copies of relevant documents;

 (5) Specifically request a ruling of the individual upon whom the protest is served;

 (6) State the form of relief requested; and

 (7) Provide all information establishing the timeliness of the protest.

 (b) Failure to comply with the above may result in dismissal of the protest without further consideration.

 (c) Bidders/offerors and contracting officers are encouraged to use alternative dispute resolution (ADR) procedures to resolve protests at any stage in the protest process. If ADR is used, the Department of Veterans Affairs will not furnish any documentation in an ADR proceeding beyond what is allowed by the Federal Acquisition Regulation.

(End of Provision)

 PLEASE NOTE: The correct mailing information for filing alternate protests is as follows:

 Deputy Assistant Secretary for Acquisition and Logistics,

 Risk Management Team, Department of Veterans Affairs

 810 Vermont Avenue, N.W.

 Washington, DC 20420

 Or for solicitations issued by the Office of Construction and Facilities Management:

 Director, Office of Construction and Facilities Management

 811 Vermont Avenue, N.W.

 Washington, DC 20420

#

# REPRESENTATIONS AND CERTIFICATIONS

## 3.1 52.203-98 PROHIBITION ON CONTRACTING WITH ENTITIES THAT REQUIRE CERTAIN INTERNAL CONFIDENTIALITY AGREEMENTS—REPRESENTATION (DEVIATION) (FEB 2015)

 (a) In accordance with section 743 of Division E, Title VII, of the Consolidated and Further Continuing Resolution Appropriations Act, 2015 (Pub. L. 113-235), Government agencies are not permitted to use funds appropriated (or otherwise made available) under that or any other Act for contracts with an entity that requires employees or subcontractors of such entity seeking to report fraud, waste, or abuse to sign internal confidentiality agreements or statements prohibiting or otherwise restricting such employees or contactors from lawfully reporting such waste, fraud, or abuse to a designated investigative or law enforcement representative of a Federal department or agency authorized to receive such information.

 (b) The prohibition in paragraph (a) of this provision does not contravene requirements applicable to Standard Form 312, Form 4414, or any other form issued by a Federal department or agency governing the nondisclosure of classified information.

 (c) *Representation*. By submission of its offer, the Offeror represents that it does not require employees or subcontractors of such entity seeking to report fraud, waste, or abuse to sign internal confidentiality agreements or statements prohibiting or otherwise restricting such employees or subcontractors from lawfully reporting such waste, fraud, or abuse to a designated investigative or law enforcement representative of a Federal department or agency authorized to receive such information.

(End of Provision)

## 3.2 52.209-5 REPRESENTATION BY CORPORATIONS REGARDING AN UNPAID TAX LIABILITY OR A FELONY CONVICTION UNDER ANY FEDERAL LAW (DEVIATION)(MAR 2012)

 (a) In accordance with Division H, sections 8124 and 8125 of P.L. 112-74 and sections 738 and 739 of P.L. 112-55 none of the funds made available by either Act may be used to enter into a contract with any corporation that—

 (1) Has an unpaid federal tax liability, unless the agency has considered suspension or debarment of the corporation and the Suspension and Debarment Official has made a determination that this action is not necessary to protect the interests of the Government.

 (2) Has a felony criminal violation under any Federal or State law within the preceding 24 months, unless the agency has considered suspension or debarment of the corporation and Suspension and Debarment Official has made a determination that this action is not necessary to protect the interests of the Government.

 (b) The Offeror represents that—

 (1) The offeror does [ ] does not [ ] have any unpaid Federal tax liability that has been assessed and that is not being paid in a timely manner pursuant to an agreement with the authority responsible for collecting the tax liability.

 (2) The offeror, its officers or agents acting on its behalf have [ ] have not [ ] been convicted of a felony criminal violation under a Federal or State law within the preceding 24 months.

(End of Provision)

## 3.3 52.204-8 ANNUAL REPRESENTATIONS AND CERTIFICATIONS (DEC 2016)

 (a)(1) The North American Industry Classification System (NAICS) code for this acquisition is 236220.

 (2) The small business size standard is $36.5 Million.

 (3) The small business size standard for a concern which submits an offer in its own name, other than on a construction or service contract, but which proposes to furnish a product which it did not itself manufacture, is 500 employees.

 (b)(1) If the provision at 52.204-7, System for Award Management, is included in this solicitation, paragraph (d) of this provision applies.

 (2) If the provision at 52.204-7 is not included in this solicitation, and the offeror is currently registered in the System for Award Management (SAM), and has completed the Representations and Certifications section of SAM electronically, the offeror may choose to use paragraph (d) of this provision instead of completing the corresponding individual representations and certifications in the solicitation. The offeror shall indicate which option applies by checking one of the following boxes:

 [ ] (i) Paragraph (d) applies.

 [ ] (ii) Paragraph (d) does not apply and the offeror has completed the individual representations and certifications in the solicitation.

 (c)(1) The following representations or certifications in SAM are applicable to this solicitation as indicated:

 (i) 52.203-2, Certificate of Independent Price Determination. This provision applies to solicitations when a firm-fixed-price contract or fixed-price contract with economic price adjustment is contemplated, unless—

 (A) The acquisition is to be made under the simplified acquisition procedures in Part 13;

 (B) The solicitation is a request for technical proposals under two-step sealed bidding procedures; or

 (C) The solicitation is for utility services for which rates are set by law or regulation.

 (ii) 52.203-11, Certification and Disclosure Regarding Payments to Influence Certain Federal Transactions. This provision applies to solicitations expected to exceed $150,000.

 (iii) 52.204-3, Taxpayer Identification. This provision applies to solicitations that do not include the provision at 52.204-7, System for Award Management.

 (iv) 52.204-5, Women-Owned Business (Other Than Small Business). This provision applies to solicitations that—

 (A) Are not set aside for small business concerns;

 (B) Exceed the simplified acquisition threshold; and

 (C) Are for contracts that will be performed in the United States or its outlying areas.

 (v) 52.209-2, Prohibition on Contracting with Inverted Domestic Corporations—Representation.

 (vi) 52.209-5, Certification Regarding Responsibility Matters. This provision applies to solicitations where the contract value is expected to exceed the simplified acquisition threshold.

 (vii) 52.209-11, Representation by Corporations Regarding Delinquent Tax Liability or a Felony Conviction under any Federal Law. This provision applies to all solicitations.

 (viii) 52.214-14, Place of Performance—Sealed Bidding. This provision applies to invitations for bids except those in which the place of performance is specified by the Government.

 (ix) 52.215-6, Place of Performance. This provision applies to solicitations unless the place of performance is specified by the Government.

 (x) 52.219-1, Small Business Program Representations (Basic & Alternate I). This provision applies to solicitations when the contract will be performed in the United States or its outlying areas.

 (A) The basic provision applies when the solicitations are issued by other than DoD, NASA, and the Coast Guard.

 (B) The provision with its Alternate I applies to solicitations issued by DoD, NASA, or the Coast Guard.

 (xi) 52.219-2, Equal Low Bids. This provision applies to solicitations when contracting by sealed bidding and the contract will be performed in the United States or its outlying areas.

 (xii) 52.222-22, Previous Contracts and Compliance Reports. This provision applies to solicitations that include the clause at 52.222-26, Equal Opportunity.

 (xiii) 52.222-25, Affirmative Action Compliance. This provision applies to solicitations, other than those for construction, when the solicitation includes the clause at 52.222-26, Equal Opportunity.

 (xiv) 52.222-38, Compliance with Veterans' Employment Reporting Requirements. This provision applies to solicitations when it is anticipated the contract award will exceed the simplified acquisition threshold and the contract is not for acquisition of commercial items.

 (xv) 52.222-57, Representation Regarding Compliance with Labor Laws (Executive Order 13673). This provision applies to solicitations expected to exceed $50 million which are issued from October 25, 2016 through April 24, 2017, and solicitations expected to exceed $500,000, which are issued after April 24, 2017.

**Note to paragraph (c)(1)(xv):** By a court order issued on October 24, 2016, 52.222-57 is enjoined indefinitely as of the date of the order. The enjoined paragraph will become effective immediately if the court terminates the injunction. At that time, DoD, GSA, and NASA will publish a document in the **Federal Register** advising the public of the termination of the injunction.

 (xvi) 52.223-1, Biobased Product Certification. This provision applies to solicitations that require the delivery or specify the use of USDA-designated items; or include the clause at 52.223-2, Affirmative Procurement of Biobased Products Under Service and Construction Contracts.

 (xvii) 52.223-4, Recovered Material Certification. This provision applies to solicitations that are for, or specify the use of, EPA-designated items.

 (xviii) 52.223-22, Public Disclosure of Greenhouse Gas Emissions and Reduction Goals--Representation. This provision applies to solicitations that include the clause at 52.204-7.)

 (xix) 52.225-2, Buy American Certificate. This provision applies to solicitations containing the clause at 52.225-1.

 (xx) 52.225-4, Buy American—Free Trade Agreements—Israeli Trade Act Certificate. (Basic, Alternates I, II, and III.) This provision applies to solicitations containing the clause at 52.225-3.

 (A) If the acquisition value is less than $25,000, the basic provision applies.

 (B) If the acquisition value is $25,000 or more but is less than $50,000, the provision with its Alternate I applies.

 (C) If the acquisition value is $50,000 or more but is less than $77,533, the provision with its Alternate II applies.

 (D) If the acquisition value is $77,533 or more but is less than $100,000, the provision with its Alternate III applies.

 (xxi) 52.225-6, Trade Agreements Certificate. This provision applies to solicitations containing the clause at 52.225-5.

 (xxii) 52.225-20, Prohibition on Conducting Restricted Business Operations in Sudan—Certification. This provision applies to all solicitations.

 (xxiii) 52.225-25, Prohibition on Contracting with Entities Engaging in Certain Activities or Transactions Relating to Iran—Representation and Certifications. This provision applies to all solicitations.

 (xxiv) 52.226-2, Historically Black College or University and Minority Institution Representation. This provision applies to solicitations for research, studies, supplies, or services of the type normally acquired from higher educational institutions.

 (A) Solicitations for research, studies, supplies, or services of the type normally acquired from higher educational institutions; and

 (B) For DoD, NASA, and Coast Guard acquisitions, solicitations that contain the clause at 52.219-23, Notice of Price Evaluation Adjustment for Small Disadvantaged Business Concerns.

 (2) The following representations or certifications are applicable as indicated by the Contracting Officer:

 [X](i) 52.204-17, Ownership or Control of Offeror.

 [X](ii) 52.204-20, Predecessor of Offeror.

 [](iii) 52.222-18, Certification Regarding Knowledge of Child Labor for Listed End Products.

 [](iv) 52.222-48, Exemption from Application of the Service Contract Labor Standards to Contracts for Maintenance, Calibration, or Repair of Certain Equipment—Certification.

 [](v) 52.222-52, Exemption from Application of the Service Contract Labor Standards to Contracts for Certain Services—Certification.

 [](vi) 52.223-9, with its Alternate I, Estimate of Percentage of Recovered Material Content for EPA-Designated Products (Alternate I only).

 [](vii) 52.227-6, Royalty Information.

 [](A) Basic.

 [](B) Alternate I.

 [](viii) 52.227-15, Representation of Limited Rights Data and Restricted Computer Software.

 (d) The offeror has completed the annual representations and certifications electronically via the SAM Web site accessed through <https://www.acquisition.gov>. After reviewing the SAM database information, the offeror verifies by submission of the offer that the representations and certifications currently posted electronically that apply to this solicitation as indicated in paragraph (c) of this provision have been entered or updated within the last 12 months, are current, accurate, complete, and applicable to this solicitation (including the business size standard applicable to the NAICS code referenced for this solicitation), as of the date of this offer and are incorporated in this offer by reference (see FAR 4.1201); except for the changes identified below [offeror to insert changes, identifying change by clause number, title, date]. These amended representation(s) and/or certification(s) are also incorporated in this offer and are current, accurate, and complete as of the date of this offer.

|  |  |  |  |
| --- | --- | --- | --- |
| FAR Clause # | Title | Date | Change |
|  |  |  |  |

 Any changes provided by the offeror are applicable to this solicitation only, and do not result in an update to the representations and certifications posted on SAM.

(End of Provision)

# GENERAL CONDITIONS

## 4.1 SBA ACT 8 (d) (13) (B)

(B) NOTICE.—

(i) IN GENERAL.—A prime contractor for a covered contract shall notify in writing the contracting officer for the covered contract if the prime contractor pays a reduced price to a subcontractor for goods and services upon completion of the responsibilities of the subcontractor or the payment to a subcontractor is more than 90 days past due for goods or services provided for the covered contract for which the Federal agency has paid the prime contractor.

(ii) CONTENTS.—A prime contractor shall include the reason for the reduction in a payment to or failure to pay a subcontractor in any notice made under clause (i).

## 4.2 DIGNITY CLAUSE FOR NCA CONTRACTS

1. Every action by contractor personnel at a National Cemetery must be performed with the special care, reverence, dignity, and respect that acknowledge the cemetery as the final resting place that commemorates the service and sacrifice those service members, Veterans, and their families made for our Nation. Critically important is the awareness, required of the contractor employees, of the remains buried in the grounds where the work is performed. The utmost care must be given to these remains and the headstones and flat grave markers that mark those gravesites and memorialize the service of individuals.

**a**. Contractors cannot walk, stand, lean, sit or jump on headstones or markers. Nor can they drive over them. Contractor personnel should use tools approved by the Contracting Officer Representative (COR), such as shovels, pry bars or pinch bars to lift flat markers out of the ground; pick axes are not an acceptable tool.

**b.** No tools, equipment or other items will be placed or leaned on headstones or markers. Once headstones/markers are removed from the socket, do not place on dirt piles or mud; they should be carefully placed on each associated gravesite and protected in such a way as to prevent any soiling and be out of the way of any other work.

**c.** Headstones shall be removed from their sockets using wooden and/or metal clamps. If metal clamps are used, the area that contacts the headstone must be protected with a rigid fabric that will prevent damage to and marking of the headstone. Clamps may be attached to a skid steer loader (i.e., Bobcat®) or similar machine to extract the headstone from the socket. When headstones are removed from their sockets, they shall be carefully stored on each associated gravesite; do not lean headstones against each other. Use care not to scratch or damage headstones in any manner. The headstones shall be laid with front inscription side up while the headstone is lying horizontally on the ground. The headstone shall be protected from direct ground contact while lying horizontally. The protection method shall be as approved by the COR and shall be free of deterioration in weather. An approved method is to support each headstone with two wood 4X4’s. Alternate methods can be approved. Cardboard shall not be used. Wood or other suitable appropriate and attractive material shall be used to keep the headstones from contact with the soil while lying horizontally during the construction period. This also shows respect towards the families visiting the gravesites and the remains that are buried.

**d.** Contractor shall be responsible for replacing damaged headstones and markers and for restoring turf damaged during performance of this work.

**e.** Additionally, should any activity result in the exposure and/or damage to any remains, container for remains (i.e., casket or urn), or outer burial container, the Contractor must contact the COR, Director/Assistant Director, and Contracting Officer (CO) for guidance.

1. Any doubts as to proper procedures shall be brought to the attention of the COR, Director/Assistant Director, and CO for guidance or resolution.
2. The **Contractor is required** to discuss the guidance with their employees **and have each employee sign a statement of compliance and deliver the signed statement to the COR before work may begin.**

## 4.3 52.252-2 CLAUSES INCORPORATED BY REFERENCE (FEB 1998)

This contract incorporates one or more clauses by reference, with the same force and effect as if they were given in full text. Upon request, the Contracting Officer will make their full text available. Also, the full text of a clause may be accessed electronically at this/these address(es):

 http://www.acquisition.gov/far/index.html

 http://www.va.gov/oal/library/vaar/

(End of Clause)

|  |  |  |  |
| --- | --- | --- | --- |
|  | **FAR Number** | **Title** | **Date** |
|  | 52.202-1 | DEFINITIONS | NOV 2013 |
|  | 52.203-3 | GRATUITIES | APR 1984 |
|  | 52.203-5 | COVENANT AGAINST CONTINGENT FEES | MAY 2014 |
|  | 52.203-6 | RESTRICTIONS ON SUBCONTRACTOR SALES TO THE GOVERNMENT ALTERNATE I (OCT 1995) | SEP 2006 |
|  | 52.203-7 | ANTI-KICKBACK PROCEDURES | MAY 2014 |
|  | 52.203-8 | CANCELLATION, RESCISSION, AND RECOVERY OF FUNDS FOR ILLEGAL OR IMPROPER ACTIVITY | MAY 2014 |
|  | 52.203-10 | PRICE OR FEE ADJUSTMENT FOR ILLEGAL OR IMPROPER ACTIVITY | MAY 2014 |
|  | 52.203-12 | LIMITATION ON PAYMENTS TO INFLUENCE CERTAIN FEDERAL TRANSACTIONS | OCT 2010 |
|  | 52.203-13 | CONTRACTOR CODE OF BUSINESS ETHICS AND CONDUCT | OCT 2015 |
|  | 52.203-14 | DISPLAY OF HOTLINE POSTER(S) | OCT 2015 |
|  | 52.203-17 | CONTRACTOR EMPLOYEE WHISTLEBLOWER RIGHTS AND REQUIREMENT TO INFORM EMPLOYEES OF WHISTLEBLOWER RIGHTS | APR 2014 |
|  | 52.204-4 | PRINTED OR COPIED DOUBLE-SIDED ON RECYCLED PAPER | MAY 2011 |
|  | 52.204-9 | PERSONAL IDENTITY VERIFICATION OF CONTRACTOR PERSONNEL | JAN 2011 |
|  | 52.204-10 | REPORTING EXECUTIVE COMPENSATION AND FIRST-TIER SUBCONTRACT AWARDS | OCT 2016 |
|  | 52.204-13 | SYSTEM FOR AWARD MANAGEMENT MAINTENANCE | OCT 2016 |
|  | 52.204-14 | SERVICE CONTRACT REPORTING REQUIREMENTS | OCT 2016 |
|  | 52.204-18 | COMMERCIAL AND GOVERNMENT ENTITY CODE MAINTENANCE | JUL 2016 |
|  | 52.209-6 | PROTECTING THE GOVERNMENT'S INTEREST WHEN SUBCONTRACTING WITH CONTRACTORS DEBARRED, SUSPENDED, OR PROPOSED FOR DEBARMENT | OCT 2015 |
|  | 52.209-9 | UPDATES OF PUBLICLY AVAILABLE INFORMATION REGARDING RESPONSIBILITY MATTERS | JUL 2013 |
|  | 52.209-10 | PROHIBITION ON CONTRACTING WITH INVERTED DOMESTIC CORPORATIONS | NOV 2015 |
|  | 52.210-1 | MARKET RESEARCH | APR 2011 |
|  | 52.211-10 | COMMENCEMENT, PROSECUTION, AND COMPLETION OF WORK ALTERNATE I (APR 1984) | APR 1984 |
|  | 52.211-12 | LIQUIDATED DAMAGES—CONSTRUCTION | SEP 2000 |
|  | 52.215-2 | AUDIT AND RECORDS—NEGOTIATION ALTERNATE I (MAR 2009) | OCT 2010 |
|  | 52.219-27 | NOTICE OF SERVICE-DISABLED VETERAN-OWNED SMALL BUSINESS SET-ASIDE | NOV 2011 |
|  | 52.222-1 | NOTICE TO THE GOVERNMENT OF LABOR DISPUTES | FEB 1997 |
|  | 52.222-3 | CONVICT LABOR | JUN 2003 |
|  | 52.222-4 | CONTRACT WORK HOURS AND SAFETY STANDARDS—OVERTIME COMPENSATION | MAY 2014 |
|  | 52.222-6 | CONSTRUCTION WAGE RATE REQUIREMENTS | MAY 2014 |
|  | 52.222-7 | WITHHOLDING OF FUNDS | MAY 2014 |
|  | 52.222-8 | PAYROLLS AND BASIC RECORDS | MAY 2014 |
|  | 52.222-9 | APPRENTICES AND TRAINEES | JUL 2005 |
|  | 52.222-10 | COMPLIANCE WITH COPELAND ACT REQUIREMENTS | FEB 1988 |
|  | 52.222-11 | SUBCONTRACTS (LABOR STANDARDS) | MAY 2014 |
|  | 52.222-12 | CONTRACT TERMINATION—DEBARMENT | MAY 2014 |
|  | 52.222-13 | COMPLIANCE WITH CONSTRUCTION WAGE RATE REQUIREMENTS AND RELATED REGULATIONS | MAY 2014 |
|  | 52.222-14 | DISPUTES CONCERNING LABOR STANDARDS | FEB 1988 |
|  | 52.222-15 | CERTIFICATION OF ELIGIBILITY | MAY 2014 |
|  | 52.222-21 | PROHIBITION OF SEGREGATED FACILITIES | APR 2015 |
|  | 52.222-26 | EQUAL OPPORTUNITY | SEP 2016 |
|  | 52.222-27 | AFFIRMATIVE ACTION COMPLIANCE REQUIREMENTS FOR CONSTRUCTION | APR 2015 |
|  | 52.222-36 | EQUAL OPPORTUNITY FOR WORKERS WITH DISABILITIES | JUL 2014 |
|  | 52.222-37 | EMPLOYMENT REPORTS ON VETERANS | FEB 2016 |
|  | 52.222-40 | NOTIFICATION OF EMPLOYEE RIGHTS UNDER THE NATIONAL LABOR RELATIONS ACT | DEC 2010 |
|  | 52.222-41 | SERVICE CONTRACT LABOR STANDARDS | MAY 2014 |
|  | 52.222-43 | FAIR LABOR STANDARDS ACT AND SERVICE CONTRACT LABOR STANDARDS—PRICE ADJUSTMENT (MULTIPLE YEAR AND OPTION CONTRACTS) | MAY 2014 |
|  | 52.222-44 | FAIR LABOR STANDARDS ACT AND SERVICE CONTRACT LABOR STANDARDS—PRICE ADJUSTMENT | MAY 2014 |
|  | 52.222-50 | COMBATING TRAFFICKING IN PERSONS | MAR 2015 |
|  | 52.222-54 | EMPLOYMENT ELIGIBILITY VERIFICATION | OCT 2015 |
|  | 52.222-55 | MINIMUM WAGES UNDER EXECUTIVE ORDER 13658 | DEC 2015 |
|  | 52.222-62 | PAID SICK LEAVE UNDER EXECUTIVE ORDER 13706 | JAN 2017 |
|  | 52.223-5 | POLLUTION PREVENTION AND RIGHT-TO-KNOW INFORMATION | MAY 2011 |
|  | 52.223-6 | DRUG-FREE WORKPLACE | MAY 2001 |
|  | 52.223-17 | AFFIRMATIVE PROCUREMENT OF EPA-DESIGNATED ITEMS IN SERVICE AND CONSTRUCTION CONTRACTS | MAY 2008 |
|  | 52.223-18 | ENCOURAGING CONTRACTOR POLICIES TO BAN TEXT MESSAGING WHILE DRIVING | AUG 2011 |
|  | 52.223-21 | FOAMS | JUN 2016 |
|  | 52.225-13 | RESTRICTIONS ON CERTAIN FOREIGN PURCHASES | JUN 2008 |
|  | 52.225-25 | PROHIBITION ON CONTRACTING WITH ENTITIES ENGAGING IN CERTAIN ACTIVITIES OR TRANSACTIONS RELATING TO IRAN—REPRESENTATION AND CERTIFICATIONS | OCT 2015 |
|  | 52.227-1 | AUTHORIZATION AND CONSENT | DEC 2007 |
|  | 52.227-2 | NOTICE AND ASSISTANCE REGARDING PATENT AND COPYRIGHT INFRINGEMENT | DEC 2007 |
|  | 52.227-4 | PATENT INDEMNITY—CONSTRUCTION CONTRACTS | DEC 2007 |
|  | 52.229-3 | FEDERAL, STATE, AND LOCAL TAXES | FEB 2013 |
|  | 52.229-4 | FEDERAL, STATE, AND LOCAL TAXES (STATE AND LOCAL ADJUSTMENTS) | FEB 2013 |
|  | 52.232-5 | PAYMENTS UNDER FIXED-PRICE CONSTRUCTION CONTRACTS | MAY 2014 |
|  | 52.232-17 | INTEREST | MAY 2014 |
|  | 52.232-18 | AVAILABILITY OF FUNDS | APR 1984 |
|  | 52.232-19 | AVAILABILITY OF FUNDS FOR THE NEXT FISCAL YEAR | APR 1984 |
|  | 52.232-23 | ASSIGNMENT OF CLAIMS | MAY 2014 |
|  | 52.232-27 | PROMPT PAYMENT FOR CONSTRUCTION CONTRACTS | MAY 2014 |
|  | 52.232-34 | PAYMENT BY ELECTRONIC FUNDS TRANSFER—OTHER THAN SYSTEM FOR AWARD MANAGEMENT | JUL 2013 |
|  | 52.232-39 | UNENFORCEABILITY OF UNAUTHORIZED OBLIGATIONS | JUN 2013 |
|  | 52.232-40 | PROVIDING ACCELERATED PAYMENTS TO SMALL BUSINESS SUBCONTRACTORS | DEC 2013 |
|  | 52.233-1 | DISPUTES | MAY 2014 |
|  | 52.233-3 | PROTEST AFTER AWARD | AUG 1996 |
|  | 52.233-4 | APPLICABLE LAW FOR BREACH OF CONTRACT CLAIM | OCT 2004 |
|  | 52.236-1 | PERFORMANCE OF WORK BY THE CONTRACTOR | APR 1984 |
|  | 52.236-2 | DIFFERING SITE CONDITIONS | APR 1984 |
|  | 52.236-3 | SITE INVESTIGATION AND CONDITIONS AFFECTING THE WORK | APR 1984 |
|  | 52.236-5 | MATERIAL AND WORKMANSHIP | APR 1984 |
|  | 52.236-6 | SUPERINTENDENCE BY THE CONTRACTOR | APR 1984 |
|  | 52.236-7 | PERMITS AND RESPONSIBILITIES | NOV 1991 |
|  | 52.236-8 | OTHER CONTRACTS | APR 1984 |
|  | 52.236-9 | PROTECTION OF EXISTING VEGETATION, STRUCTURES, EQUIPMENT, UTILITIES, AND IMPROVEMENTS | APR 1984 |
|  | 52.236-10 | OPERATIONS AND STORAGE AREAS | APR 1984 |
|  | 52.236-11 | USE AND POSSESSION PRIOR TO COMPLETION | APR 1984 |
|  | 52.236-12 | CLEANING UP | APR 1984 |
|  | 52.236-13 | ACCIDENT PREVENTION | NOV 1991 |
|  | 52.236-15 | SCHEDULES FOR CONSTRUCTION CONTRACTS | APR 1984 |
|  | 52.236-17 | LAYOUT OF WORK | APR 1984 |
|  | 52.236-21 | SPECIFICATIONS AND DRAWINGS FOR CONSTRUCTION | FEB 1997 |
|  | 52.236-26 | PRECONSTRUCTION CONFERENCE | FEB 1995 |
|  | 52.242-13 | BANKRUPTCY | JUL 1995 |
|  | 52.242-14 | SUSPENSION OF WORK | APR 1984 |
|  | 52.243-4 | CHANGES | JUN 2007 |
|  | 52.243-5 | CHANGES AND CHANGED CONDITIONS | APR 1984 |
|  | 52.244-2 | SUBCONTRACTS | OCT 2010 |
|  | 52.244-5 | COMPETITION IN SUBCONTRACTING | DEC 1996 |
|  | 52.244-6 | SUBCONTRACTS FOR COMMERCIAL ITEMS | JAN 2017 |
|  | 52.246-12 | INSPECTION OF CONSTRUCTION | AUG 1996 |
|  | 52.246-13 | INSPECTION—DISMANTLING, DEMOLITION, OR REMOVAL OF IMPROVEMENTS | AUG 1996 |
|  | 52.246-21 | WARRANTY OF CONSTRUCTION | MAR 1994 |
|  | 52.248-3 | VALUE ENGINEERING—CONSTRUCTION | OCT 2015 |
|  | 52.249-2 | TERMINATION FOR CONVENIENCE OF THE GOVERNMENT (FIXED PRICE) ALTERNATE I (SEPT 1996) | APR 2012 |
|  | 52.249-3 | TERMINATION FOR CONVENIENCE OF THE GOVERNMENT (DISMANTLING, DEMOLITION, OR REMOVAL OF IMPROVEMENTS) | APR 2012 |
|  | 52.249-10 | DEFAULT (FIXED-PRICE CONSTRUCTION) | APR 1984 |
|  | 52.253-1 | COMPUTER GENERATED FORMS | JAN 1991 |

## 4.4 52.203-99 PROHIBITION ON CONTRACTING WITH ENTITIES THAT REQUIRE CERTAIN INTERNAL CONFIDENTIALITY AGREEMENTS (DEVIATION) (FEB 2015)

 (a) The Contractor shall not require employees or contractors seeking to report fraud, waste, or abuse to sign or comply with internal confidentiality agreements or statements prohibiting or otherwise restricting such employees or subcontractors from lawfully reporting such waste, fraud, or abuse to a designated investigative or law enforcement representative of a Federal department or agency authorized to receive such information.

 (b) The contractor shall notify employees that the prohibitions and restrictions of any internal confidentiality agreements covered by this clause are no longer in effect.

 (c) The prohibition in paragraph (a) of this clause does not contravene requirements applicable to Standard Form 312, Form 4414, or any other form issued by a Federal department or agency governing the nondisclosure of classified information.

 (d)(1) In accordance with section 743 of Division E, Title VII, of the Consolidated and Further Continuing Resolution Appropriations Act, 2015 (Pub. L. 113-235), use of funds appropriated (or otherwise made available) under that or any other Act may be prohibited, if the Government determines that the Contractor is not in compliance with the provisions of this clause.

 (2) The Government may seek any available remedies in the event the contractor fails to comply with the provisions of this clause.

(End of Clause)

## 4.5 52.204-19 INCORPORATION BY REFERENCE OF REPRESENTATIONS AND CERTIFICATIONS (DEC 2014)

 The Contractor's representations and certifications, including those completed electronically via the System for Award Management (SAM), are incorporated by reference into the contract.

(End of Clause)

## 4.6 52.217-9 OPTION TO EXTEND THE TERM OF THE CONTRACT (MAR 2000)

 (a) The Government may extend the term of this contract by written notice to the Contractor within; provided that the Government gives the Contractor a preliminary written notice of its intent to extend at least days before the contract expires. The preliminary notice does not commit the Government to an extension.

 (b) If the Government exercises this option, the extended contract shall be considered to include this option clause.

 (c) The total duration of this contract, including the exercise of any options under this clause, shall not exceed one (1) year.

(End of Clause)

## 4.7 52.219-28 POST-AWARD SMALL BUSINESS PROGRAM REREPRESENTATION (JUL 2013)

 (a) *Definitions.* As used in this clause—

 *Long-term contract* means a contract of more than five years in duration, including options. However, the term does not include contracts that exceed five years in duration because the period of performance has been extended for a cumulative period not to exceed six months under the clause at 52.217-8, Option to Extend Services, or other appropriate authority.

 *Small business concern* means a concern, including its affiliates, that is independently owned and operated, not dominant in the field of operation in which it is bidding on Government contracts, and qualified as a small business under the criteria in 13 CFR part 121 and the size standard in paragraph (c) of this clause. Such a concern is "not dominant in its field of operation" when it does not exercise a controlling or major influence on a national basis in a kind of business activity in which a number of business concerns are primarily engaged. In determining whether dominance exists, consideration shall be given to all appropriate factors, including volume of business, number of employees, financial resources, competitive status or position, ownership or control of materials, processes, patents, license agreements, facilities, sales territory, and nature of business activity.

 (b) If the Contractor represented that it was a small business concern prior to award of this contract, the Contractor shall rerepresent its size status according to paragraph (e) of this clause or, if applicable, paragraph (g) of this clause, upon the occurrence of any of the following:

 (1) Within 30 days after execution of a novation agreement or within 30 days after modification of the contract to include this clause, if the novation agreement was executed prior to inclusion of this clause in the contract.

 (2) Within 30 days after a merger or acquisition that does not require a novation or within 30 days after modification of the contract to include this clause, if the merger or acquisition occurred prior to inclusion of this clause in the contract.

 (3) For long-term contracts—

 (i) Within 60 to 120 days prior to the end of the fifth year of the contract; and

 (ii) Within 60 to 120 days prior to the date specified in the contract for exercising any option thereafter.

 (c) The Contractor shall rerepresent its size status in accordance with the size standard in effect at the time of this rerepresentation that corresponds to the North American Industry Classification System (NAICS) code assigned to this contract. The small business size standard corresponding to this NAICS code can be found at <http://www.sba.gov/content/table-small-business-size-standards>.

 (d) The small business size standard for a Contractor providing a product which it does not manufacture itself, for a contract other than a construction or service contract, is 500 employees.

 (e) Except as provided in paragraph (g) of this clause, the Contractor shall make the representation required by paragraph (b) of this clause by validating or updating all its representations in the Representations and Certifications section of the System for Award Management (SAM) and its other data in SAM, as necessary, to ensure that they reflect the Contractor's current status. The Contractor shall notify the contracting office in writing within the timeframes specified in paragraph (b) of this clause that the data have been validated or updated, and provide the date of the validation or update.

 (f) If the Contractor represented that it was other than a small business concern prior to award of this contract, the Contractor may, but is not required to, take the actions required by paragraphs (e) or (g) of this clause.

 (g) If the Contractor does not have representations and certifications in SAM, or does not have a representation in SAM for the NAICS code applicable to this contract, the Contractor is required to complete the following rerepresentation and submit it to the contracting office, along with the contract number and the date on which the rerepresentation was completed:

 The Contractor represents that it [ ] is, [ ] is not a small business concern under NAICS Code 236220 assigned to contract number .

[Co*ntractor to sign and date and insert authorized signer's name and title*].

(End of Clause)

## 4.8 52.222-30 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (NONE OR SEPARATELY SPECIFIED METHOD) (MAY 2014)

 (a) The wage determination issued under the Construction Wage Rate Requirements statute by the Administrator, Wage and Hour Division, Employment Standards Administration, U.S. Department of Labor, that is effective for an option to extend the term of the contract, will apply to that option period.

 (b) The Contracting Officer will make no adjustment in contract price, other than provided for elsewhere in this contract, to cover any increases or decreases in wages and benefits as a result of—

 (1) Incorporation of the Department of Labor's wage determination applicable at the exercise of the option to extend the term of the contract;

 (2) Incorporation of a wage determination otherwise applied to the contract by operation of law; or

 (3) An increase in wages and benefits resulting from any other requirement applicable to workers subject to the Construction Wage Rate Requirements statute.

(End of Clause)

## 4.9 52.222-31 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (PERCENTAGE METHOD) (MAY 2014)

 (a) The wage determination issued under the Construction Wage Rate Requirements statute by the Administrator, Wage and Hour Division, Employment Standards Administration, U.S. Department of Labor, that is effective for an option to extend the term of the contract, will apply to that option period.

 (b) The Contracting Officer will adjust the portion of the contract price or contract unit price(s) containing the labor costs subject to the Construction Wage Rate Requirements statute to provide for an increase in wages and fringe benefits at the exercise of each option to extend the term of the contract in accordance with the following procedures:

 (1) The Contracting Officer has determined that the portion of the contract price or contract unit price(s) containing labor costs subject to the Construction Wage Rate Requirements statute is percent.

 (2) The Contracting Officer will increase the portion of the contract price or contract unit price(s) containing the labor costs subject to the Construction Wage Rate Requirements statute by the percentage rate published in .

 (c) The Contracting Officer will make the price adjustment at the exercise of each option to extend the term of the contract. This adjustment is the only adjustment that the Contracting Officer will make to cover any increases in wages and benefits as a result of—

 (1) Incorporation of the Department of Labor's wage determination applicable at the exercise of the option to extend the term of the contract;

 (2) Incorporation of a wage determination otherwise applied to the contract by operation of law; or

 (3) An increase in wages and benefits resulting from any other requirement applicable to workers subject to the Construction Wage Rate Requirements statute.

(End of Clause)

## 4.10 52.222-32 CONSTRUCTION WAGE RATE REQUIREMENTS—PRICE ADJUSTMENT (ACTUAL METHOD) (MAY 2014)

 (a) The wage determination issued under the Construction Wage Rate Requirements statute by the Administrator, Wage and Hour Division, Employment Standards Administration, U.S. Department of Labor, that is effective for an option to extend the term of the contract, will apply to that option period.

 (b)(1) The Contractor states that if the prices in this contract contain an allowance for wage or benefit increases, such allowance will not be included in any request for contract price adjustment submitted under this clause.

 (2) The Contractor shall provide with each request for contract price adjustment under this clause a statement that the prices in the contract do not include any allowance for any increased cost for which adjustment is being requested.

 (c) The Contracting Officer will adjust the contract price or contract unit price labor rates to reflect the Contractor's actual increase or decrease in wages and fringe benefits to the extent that the increase is made to comply with, or the decrease is voluntarily made by the Contractor as a result of—

 (1) Incorporation of the Department of Labor's Construction Wage Rate Requirements wage determination applicable at the exercise of an option to extend the term of the contract; or

 (2) Incorporation of a Construction Wage Rate Requirements wage determination otherwise applied to the contract by operation of law.

 (d) Any adjustment will be limited to increases or decreases in wages and fringe benefits as described in paragraph (c) of this clause, and the accompanying increases or decreases in social security and unemployment taxes and workers' compensation insurance, but will not otherwise include any amount for general and administrative costs, overhead, or profit.

 (e) The Contractor shall notify the Contracting Officer of any increase claimed under this clause within 30 days after receiving a revised wage determination unless this notification period is extended in writing by the Contracting Officer. The Contractor shall notify the Contracting Officer promptly of any decrease under this clause, but nothing in this clause precludes the Government from asserting a claim within the period permitted by law. The notice shall contain a statement of the amount claimed and any relevant supporting data, including payroll records that the Contracting Officer may reasonably require. Upon agreement of the parties, the Contracting Officer will modify the contract price or contract unit price in writing. The Contractor shall continue performance pending agreement on or determination of any such adjustment and its effective date.

 (f) Contract price adjustment computations shall be computed as follows:

 (1) *Computation for contract unit price per single craft hour for schedule of indefinite-quantity work*. For each labor classification, the difference between the actual wage and benefit rates (combined) paid and the wage and benefit rates (combined) required by the new wage determination shall be added to the original contract unit price if the difference results in a combined increase. If the difference computed results in a combined decrease, the contract unit price shall be decreased by that amount if the Contractor provides notification as provided in paragraph (e) of this clause.

 (2) *Computation for contract unit price containing multiple craft hours for schedule of indefinite-quantity work*. For each labor classification, the difference between the actual wage and benefit rates (combined) paid and the wage and benefit rates (combined) required by the new wage determination shall be multiplied by the actual number of hours expended for each craft involved in accomplishing the unit-priced work item. The product of this computation will then be divided by the actual number of units ordered in the preceding contract period. The total of these computations for each craft will be added to the current contract unit price to obtain the new contract unit price. The extended amount for the contract line item will be obtained by multiplying the new unit price by the estimated quantity. If actual hours are not available from the preceding contract period for computation of the adjustment for a specific contract unit of work, the Contractor, in agreement with the Contracting Officer, shall estimate the total hours per craft per contract unit of work.

Example: Asphalt Paving—Current Price $3.38 per Square Yard

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **DBA Craft** | **New WD** | **Hourly Rate Paid** | **Diff** | **Actual Hrs** | **Actual units (sq. yard)** | **Increase/sq. yard** |
| Equip. Opr. | $18.50 | $18.00 | $.50 | 600 hrs. | 3,000 sq. yrd. | $.10 |
| Truck Driver | $19.00 | $18.25 | $.75 | 525 hrs. | 3,000 sq. yrd. | $.13 |
| Laborer | $11.50 | $11.25 | $.25 | 750 hrs. | 3,000 sq. yrd. | $.06 |
| Total increase per square yard = | $.29 |

\* Note: Adjustment for labor rate increases or decreases may be accompanied by social security and unemployment taxes and workers’ compensation insurance.

|  |  |
| --- | --- |
| Current unit price (per square yard) | $3.38 per square yard |
| Add DBA price adj. | + .29 |
| New unit price (per square yard) | $3.67 per square yard |

(End of Clause)

## 4.11 52.222-35 EQUAL OPPORTUNITY FOR VETERANS (OCT 2015)

 (a) *Definitions*. As used in this clause—

 “Active duty wartime or campaign badge veteran,” “Armed Forces service medal veteran,” “disabled veteran,” “protected veteran,” “qualified disabled veteran,” and “recently separated veteran” have the meanings given at FAR 22.1301.

 (b) *Equal opportunity clause*. The Contractor shall abide by the requirements of the equal opportunity clause at 41 CFR 60-300.5(a), as of March 24, 2014. This clause prohibits discrimination against qualified protected veterans, and requires affirmative action by the Contractor to employ and advance in employment qualified protected veterans.

 (c) *Subcontracts*. The Contractor shall insert the terms of this clause in subcontracts of $150,000 or more unless exempted by rules, regulations, or orders of the Secretary of Labor. The Contractor shall act as specified by the Director, Office of Federal Contract Compliance Programs, to enforce the terms, including action for noncompliance. Such necessary changes in language may be made as shall be appropriate to identify properly the parties and their undertakings.

(End of Clause)

## 4.12 52.222-42 STATEMENT OF EQUIVALENT RATES FOR FEDERAL HIRES (MAY 2014)

 In compliance with the Service Contract Labor Standards statute and the regulations of the Secretary of Labor (29 CFR part 4), this clause identifies the classes of service employees expected to be employed under the contract and states the wages and fringe benefits payable to each if they were employed by the contracting agency subject to the provisions of 5 U.S.C. 5341 or 5332.

This Statement is for Information Only:

It is not a Wage Determination

|  |  |
| --- | --- |
| **Employee Class** | **Monetary Wage—Fringe Benefits** |
|  |  |
|  |  |
|  |  |
|  |  |

(End of Clause)

## 4.13 52.225-9 BUY AMERICAN—CONSTRUCTION MATERIALS (MAY 2014)

 (a) *Definitions.* As used in this clause—

 "Commercially available off-the-shelf (COTS) item"—

 (1) Means any item of supply (including construction material) that is—

 (i) A commercial item (as defined in paragraph (1) of the definition at FAR 2.101);

 (ii) Sold in substantial quantities in the commercial marketplace; and

 (iii) Offered to the Government, under a contract or subcontract at any tier, without modification, in the same form in which it is sold in the commercial marketplace; and

 (2) Does not include bulk cargo, as defined in 46 U.S.C. 40102(4), such as agricultural products and petroleum products.

 "Component" means any article, material, or supply incorporated directly into construction material.

 "Construction material" means an article, material, or supply brought to the construction site by the Contractor or a subcontractor for incorporation into the building or work. The term also includes an item brought to the site preassembled from articles, materials, or supplies. However, emergency life safety systems, such as emergency lighting, fire alarm, and audio evacuation systems, that are discrete systems incorporated into a public building or work and that are produced as complete systems, are evaluated as a single and distinct construction material regardless of when or how the individual parts or components of those systems are delivered to the construction site. Materials purchased directly by the Government are supplies, not construction material.

 "Cost of components" means—

 (1) For components purchased by the Contractor, the acquisition cost, including transportation costs to the place of incorporation into the end product (whether or not such costs are paid to a domestic firm), and any applicable duty (whether or not a duty-free entry certificate is issued); or

 (2) For components manufactured by the Contractor, all costs associated with the manufacture of the component, including transportation costs as described in paragraph (1) of this definition, plus allocable overhead costs, but excluding profit. Cost of components does not include any costs associated with the manufacture of the construction material.

 "Domestic construction material" means—

 (1) An unmanufactured construction material mined or produced in the United States;

 (2) A construction material manufactured in the United States, if—

 (i) The cost of its components mined, produced, or manufactured in the United States exceeds 50 percent of the cost of all its components. Components of foreign origin of the same class or kind for which nonavailability determinations have been made are treated as domestic; or

 (ii) The construction material is a COTS item.

 "Foreign construction material" means a construction material other than a domestic construction material.

 "United States" means the 50 States, the District of Columbia, and outlying areas.

 (b) Domestic preference.

 (1) This clause implements 41 U.S.C. chapter 83, Buy American, by providing a preference for domestic construction material. In accordance with 41 U.S.C. 1907, the component test of the Buy American statute is waived for construction material that is a COTS item. (See FAR 12.505(a)(2)). The Contractor shall use only domestic construction material in performing this contract, except as provided in paragraphs (b)(2) and (b)(3) of this clause.

 (2) This requirement does not apply to information technology that is a commercial item or to the construction materials or components listed by the Government as follows:

 NONE

 (3) The Contracting Officer may add other foreign construction material to the list in paragraph (b)(2) of this clause if the Government determines that—

 (i) The cost of domestic construction material would be unreasonable. The cost of a particular domestic construction material subject to the requirements of the Buy American statute is unreasonable when the cost of such material exceeds the cost of foreign material by more than 6 percent;

 (ii) The application of the restriction of the Buy American statute to a particular construction material would be impracticable or inconsistent with the public interest; or

 (iii) The construction material is not mined, produced, or manufactured in the United States in sufficient and reasonably available commercial quantities of a satisfactory quality.

 (c) Request for determination of inapplicability of the Buy American statute.

 (1)(i) Any Contractor request to use foreign construction material in accordance with paragraph (b)(3) of this clause shall include adequate information for Government evaluation of the request, including—

 (A) A description of the foreign and domestic construction materials;

 (B) Unit of measure;

 (C) Quantity;

 (D) Price;

 (E) Time of delivery or availability;

 (F) Location of the construction project;

 (G) Name and address of the proposed supplier; and

 (H) A detailed justification of the reason for use of foreign construction materials cited in accordance with paragraph (b)(3) of this clause.

 (ii) A request based on unreasonable cost shall include a reasonable survey of the market and a completed price comparison table in the format in paragraph (d) of this clause.

 (iii) The price of construction material shall include all delivery costs to the construction site and any applicable duty (whether or not a duty-free certificate may be issued).

 (iv) Any Contractor request for a determination submitted after contract award shall explain why the Contractor could not reasonably foresee the need for such determination and could not have requested the determination before contract award. If the Contractor does not submit a satisfactory explanation, the Contracting Officer need not make a determination.

 (2) If the Government determines after contract award that an exception to the Buy American statute applies and the Contracting Officer and the Contractor negotiate adequate consideration, the Contracting Officer will modify the contract to allow use of the foreign construction material. However, when the basis for the exception is the unreasonable price of a domestic construction material, adequate consideration is not less than the differential established in paragraph (b)(3)(i) of this clause.

 (3) Unless the Government determines that an exception to the Buy American statute applies, use of foreign construction material is noncompliant with the Buy American statute.

 (d) *Data.* To permit evaluation of requests under paragraph (c) of this clause based on unreasonable cost, the Contractor shall include the following information and any applicable supporting data based on the survey of suppliers:

FOREIGN AND DOMESTIC CONSTRUCTION MATERIALS PRICE COMPARISON

|  |  |  |  |
| --- | --- | --- | --- |
| **Construction Material Description** | **Unit of Measure** | **Quantity** | **Price (Dollars)\*** |
| Item 1: |
| Foreign Construction Material |  |  |  |
| Domestic Construction Material |  |  |  |
| Item 2: |
| Foreign Construction Material |  |  |  |
| Domestic Construction Material |  |  |  |

[List name, address, telephone number, and contact for suppliers surveyed Attach copy of response; if oral, attach summary.]

[Include other applicable supporting information.]

[\*Include all delivery costs to the construction site and any applicable duty (whether or not a duty-free entry certificate is issued).]

(End of Clause)

## 4.14 52.225-11 BUY AMERICAN—CONSTRUCTION MATERIALS UNDER TRADE AGREEMENTS (OCT 2016)

 (a) *Definitions.* As used in this clause—

 "Caribbean Basin country construction material" means a construction material that—

 (1) Is wholly the growth, product, or manufacture of a Caribbean Basin country; or

 (2) In the case of a construction material that consists in whole or in part of materials from another country, has been substantially transformed in a Caribbean Basin country into a new and different construction material distinct from the materials from which it was transformed.

 "Commercially available off-the-shelf (COTS) item"— (1) Means any item of supply (including construction material) that is—

 (i) A commercial item (as defined in paragraph (1) of the definition at FAR 2.101);

 (ii) Sold in substantial quantities in the commercial marketplace; and

 (iii) Offered to the Government, under a contract or subcontract at any tier, without modification, in the same form in which it is sold in the commercial marketplace; and

 (2) Does not include bulk cargo, as defined in 46 U.S.C. 40102(4), such as agricultural products and petroleum products.

 "Component" means an article, material, or supply incorporated directly into a construction material.

 "Construction material" means an article, material, or supply brought to the construction site by the Contractor or subcontractor for incorporation into the building or work. The term also includes an item brought to the site preassembled from articles, materials, or supplies. However, emergency life safety systems, such as emergency lighting, fire alarm, and audio evacuation systems, that are discrete systems incorporated into a public building or work and that are produced as complete systems, are evaluated as a single and distinct construction material regardless of when or how the individual parts or components of those systems are delivered to the construction site. Materials purchased directly by the Government are supplies, not construction material.

 "Cost of components" means—

 (1) For components purchased by the Contractor, the acquisition cost, including transportation costs to the place of incorporation into the construction material (whether or not such costs are paid to a domestic firm), and any applicable duty (whether or not a duty-free entry certificate is issued); or

 (2) For components manufactured by the Contractor, all costs associated with the manufacture of the component, including transportation costs as described in paragraph (1) of this definition, plus allocable overhead costs, but excluding profit. Cost of components does not include any costs associated with the manufacture of the construction material.

 "Designated country" means any of the following countries:

 (1) A World Trade Organization Government Procurement Agreement (WTO GPA) country (Armenia, Aruba, Austria, Belgium, Bulgaria, Canada, Croatia, Cyprus, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hong Kong, Hungary, Iceland, Ireland, Israel, Italy, Japan, Korea (Republic of), Latvia, Liechtenstein, Lithuania, Luxembourg, Malta, Moldova, Montenegro, Netherlands, New Zealand, Norway, Poland, Portugal, Romania, Singapore, Slovak Republic, Slovenia, Spain, Sweden, Switzerland, Taiwan, Ukraine, or United Kingdom);

 (2) A Free Trade Agreement (FTA) country (Australia, Bahrain, Canada, Chile, Colombia, Costa Rica, Dominican Republic, El Salvador, Guatemala, Honduras, Korea (Republic of), Mexico, Morocco, Nicaragua, Oman, Panama, Peru, or Singapore);

 (3) A least developed country (Afghanistan, Angola, Bangladesh, Benin, Bhutan, Burkina Faso, Burundi, Cambodia, Central African Republic, Chad, Comoros, Democratic Republic of Congo, Djibouti, Equatorial Guinea, Eritrea, Ethiopia, Gambia, Guinea, Guinea-Bissau, Haiti, Kiribati, Laos, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mozambique, Nepal, Niger, Rwanda, Samoa, Sao Tome and Principe, Senegal, Sierra Leone, Solomon Islands, Somalia, South Sudan, Tanzania, Timor-Leste, Togo, Tuvalu, Uganda, Vanuatu, Yemen, or Zambia); or

 (4) A Caribbean Basin country (Antigua and Barbuda, Aruba, Bahamas, Barbados, Belize, Bonaire, British Virgin Islands, Curacao, Dominica, Grenada, Guyana, Haiti, Jamaica, Montserrat, Saba, St. Kitts and Nevis, St. Lucia, St. Vincent and the Grenadines, Sint Eustatius, Sint Maarten, or Trinidad and Tobago).

 "Designated country construction material" means a construction material that is a WTO GPA country construction material, an FTA country construction material, a least developed country construction material, or a Caribbean Basin country construction material.

 "Domestic construction material" means—

 (1) An unmanufactured construction material mined or produced in the United States;

 (2) A construction material manufactured in the United States, if—

 (i) The cost of its components mined, produced, or manufactured in the United States exceeds 50 percent of the cost of all its components. Components of foreign origin of the same class or kind for which nonavailability determinations have been made are treated as domestic; or

 (ii) The construction material is a COTS item.

 "Foreign construction material" means a construction material other than a domestic construction material.

 "Free Trade Agreement country construction material" means a construction material that—

 (1) Is wholly the growth, product, or manufacture of a Free Trade Agreement (FTA) country; or

 (2) In the case of a construction material that consists in whole or in part of materials from another country, has been substantially transformed in a FTA country into a new and different construction material distinct from the materials from which it was transformed.

 "Least developed country construction material" means a construction material that—

 (1) Is wholly the growth, product, or manufacture of a least developed country; or

 (2) In the case of a construction material that consists in whole or in part of materials from another country, has been substantially transformed in a least developed country into a new and different construction material distinct from the materials from which it was transformed.

 "United States" means the 50 States, the District of Columbia, and outlying areas.

 "WTO GPA country construction material" means a construction material that—

 (1) Is wholly the growth, product, or manufacture of a WTO GPA country; or

 (2) In the case of a construction material that consists in whole or in part of materials from another country, has been substantially transformed in a WTO GPA country into a new and different construction material distinct from the materials from which it was transformed.

 (b) Construction materials.

 (1) This clause implements 41 U.S.C. chapter 83, Buy American, by providing a preference for domestic construction material. In accordance with 41 U.S.C. 1907, the component test of the Buy American statute is waived for construction material that is a COTS item. (See FAR 12.505(a)(2)). In addition, the Contracting Officer has determined that the WTO GPA and Free Trade Agreements (FTAs) apply to this acquisition. Therefore, the Buy American restrictions are waived for designated country construction materials.

 (2) The Contractor shall use only domestic or designated country construction material in performing this contract, except as provided in paragraphs (b)(3) and (b)(4) of this clause.

 (3) The requirement in paragraph (b)(2) of this clause does not apply to information technology that is a commercial item or to the construction materials or components listed by the Government as follows:

 NONE

 (4) The Contracting Officer may add other foreign construction material to the list in paragraph (b)(3) of this clause if the Government determines that—

 (i) The cost of domestic construction material would be unreasonable. The cost of a particular domestic construction material subject to the restrictions of the Buy American statute is unreasonable when the cost of such material exceeds the cost of foreign material by more than 6 percent;

 (ii) The application of the restriction of the Buy American statute to a particular construction material would be impracticable or inconsistent with the public interest; or

 (iii) The construction material is not mined, produced, or manufactured in the United States in sufficient and reasonably available commercial quantities of a satisfactory quality.

 (c) Request for determination of inapplicability of the Buy American statute.

 (1)(i) Any Contractor request to use foreign construction material in accordance with paragraph (b)(4) of this clause shall include adequate information for Government evaluation of the request, including—

 (A) A description of the foreign and domestic construction materials;

 (B) Unit of measure;

 (C) Quantity;

 (D) Price;

 (E) Time of delivery or availability;

 (F) Location of the construction project;

 (G) Name and address of the proposed supplier; and

 (H) A detailed justification of the reason for use of foreign construction materials cited in accordance with paragraph (b)(3) of this clause.

 (ii) A request based on unreasonable cost shall include a reasonable survey of the market and a completed price comparison table in the format in paragraph (d) of this clause.

 (iii) The price of construction material shall include all delivery costs to the construction site and any applicable duty (whether or not a duty-free certificate may be issued).

 (iv) Any Contractor request for a determination submitted after contract award shall explain why the Contractor could not reasonably foresee the need for such determination and could not have requested the determination before contract award. If the Contractor does not submit a satisfactory explanation, the Contracting Officer need not make a determination.

 (2) If the Government determines after contract award that an exception to the Buy American statute applies and the Contracting Officer and the Contractor negotiate adequate consideration, the Contracting Officer will modify the contract to allow use of the foreign construction material. However, when the basis for the exception is the unreasonable price of a domestic construction material, adequate consideration is not less than the differential established in paragraph (b)(4)(i) of this clause.

 (3) Unless the Government determines that an exception to the Buy American statute applies, use of foreign construction material is noncompliant with the Buy American statute.

 (d) *Data.* To permit evaluation of requests under paragraph (c) of this clause based on unreasonable cost, the Contractor shall include the following information and any applicable supporting data based on the survey of suppliers:

Foreign and Domestic Construction Materials Price Comparison

|  |  |  |  |
| --- | --- | --- | --- |
| **Construction Material Description** | **Unit of Measure** | **Quantity** | **Price (Dollars)\*** |
| Item 1: |
| Foreign Construction Material |  |  |  |
| Domestic Construction Material |  |  |  |
| Item 2: |
| Foreign Construction Material |  |  |  |
| Domestic Construction Material |  |  |  |

[List name, address, telephone number, and contact for suppliers surveyed. Attach copy of response; if oral, attach summary.]

[Include other applicable supporting information.]

[\* Include all delivery costs to the construction site and any applicable duty (whether or not a duty-free entry certificate is issued).]

(End of Clause)

## 4.15 52.236-27 SITE VISIT (CONSTRUCTION) (FEB 1995) ALTERNATE I (FEB 1995)

 (a) The clauses at 52.236-2, Differing Site Conditions, and 52.236-3, Site Investigations and Conditions Affecting the Work, will be included in any contract awarded as a result of this solicitation. Accordingly, offerors or quoters are urged and expected to inspect the site where the work will be performed.

 (b) An organized site visit has been scheduled for—

 (c) Participants will meet at—

(End of Provision)

## 4.16 VAAR 852.203-70 COMMERCIAL ADVERTISING (JAN 2008)

 The bidder or offeror agrees that if a contract is awarded to him/her, as a result of this solicitation, he/she will not advertise the award of the contract in his/her commercial advertising in such a manner as to state or imply that the Department of Veterans Affairs endorses a product, project or commercial line of endeavor.

(End of Clause)

## 4.17 VAAR 852.203-71 DISPLAY OF DEPARTMENT OF VETERAN AFFAIRS HOTLINE POSTER (DEC 1992)

 (a) Except as provided in paragraph (c) below, the Contractor shall display prominently, in common work areas within business segments performing work under VA contracts, Department of Veterans Affairs Hotline posters prepared by the VA Office of Inspector General.

 (b) Department of Veterans Affairs Hotline posters may be obtained from the VA Office of Inspector General (53E), P.O. Box 34647, Washington, DC 20043-4647.

 (c) The Contractor need not comply with paragraph (a) above if the Contractor has established a mechanism, such as a hotline, by which employees may report suspected instances of improper conduct, and instructions that encourage employees to make such reports.

(End of Clause)

## 4.18 VAAR 852.211-74 LIQUIDATED DAMAGES (JAN 2008)

 If any unit of the work contracted for is accepted in advance of the whole, the rate of liquidated damages assessed will be in the ratio that the value of the unaccepted work bears to the total amount of the contract. If a separate price for unaccepted work has not been stated in the contractor's bid, determination of the value thereof will be made from schedules of costs furnished by the contractor and approved by the contracting officer, as specified elsewhere in the contract.

(End of Clause)

## 4.19 VAAR 852.219-10 VA NOTICE OF TOTAL SERVICE-DISABLED VETERAN-OWNED SMALL BUSINESS SET-ASIDE (JUL 2016)(DEVIATION)

 (a) *Definition.* For the Department of Veterans Affairs, “Service-disabled veteran-owned small business concern or SDVSOB”:

 (1) Means a small business concern:

 (i) Not less than 51 percent of which is owned by one or more service-disabled veterans or, in the case of any publicly owned business, not less than 51 percent of the stock of which is owned by one or more service-disabled veterans or eligible surviving spouses (see VAAR 802.201 Surviving Spouse definition);

 (ii) The management and daily business operations of which are controlled by one or more service-disabled veterans (or eligible surviving spouses) or, in the case of a service-disabled veteran with permanent and severe disability, the spouse or permanent caregiver of such veteran;

 (iii) The business meets Federal small business size standards for the applicable North American Industry Classification System (NAICS) code identified in the solicitation document;

 (iv) The business has been verified for ownership and control pursuant to 38 CFR 74 and is so listed in the Vendor Information Pages database, (<https://www.vip.vetbiz.gov>); and

 (v) The business will comply with subcontracting limitations in 13 CFR 125.6, as applicable

 (2) “Service-disabled veteran” means a veteran, as defined in 38 U.S.C. 101(2), with a disability that is service-connected, as defined in 38 U.S.C. 101(16).

 (b) *General.*

 (1) Offers are solicited only from verified service-disabled veteran-owned small business concerns. Offers received from concerns that are not verified service-disabled veteran-owned small business concerns shall not be considered.

 (2) Any award resulting from this solicitation shall be made to a verified service-disabled veteran-owned small business concern.

 (c) *Agreement.* A service-disabled veteran-owned small business concern agrees that in the performance of the contract, the concern will comply with the limitation on subcontracting requirements in 13 CFR §125.6.

 (d) A joint venture may be considered a service-disabled veteran owned small business concern if the joint venture complies with the requirements in 13 CFR 125.15, provided that any reference therein to SDVO SBC is to be construed to apply to a VA verified SDVOSB as appropriate.

 (e) Any service-disabled veteran-owned small business concern (non-manufacturer) must meet the requirements in FAR 19.102(f) of the Federal Acquisition Regulation to receive a benefit under this program.

(End of Clause)

## 4.20 VAAR 852.228-70 BOND PREMIUM ADJUSTMENT (JAN 2008)

When net changes in original contract price affect the premium of a Corporate Surety Bond by $5 or more, the Government, in determining the basis for final settlement, will provide for bond premium adjustment computed at the rate shown in the bond.

(End of Clause)

## 4.21 VAAR 852.232-72 ELECTRONIC SUBMISSION OF PAYMENT REQUESTS (NOV 2012)

 (a) *Definitions.* As used in this clause—

 (1) *Contract financing payment* has the meaning given in FAR 32.001.

 (2) *Designated agency office* has the meaning given in 5 CFR 1315.2(m).

 (3) *Electronic form* means an automated system transmitting information electronically according to the

Accepted electronic data transmission methods and formats identified in paragraph (c) of this clause. Facsimile, email, and scanned documents are not acceptable electronic forms for submission of payment requests.

 (4) *Invoice payment* has the meaning given in FAR 32.001.

 (5) *Payment request* means any request for contract financing payment or invoice payment submitted by the contractor under this contract.

 (b) *Electronic payment requests.* Except as provided in paragraph (e) of this clause, the contractor shall submit payment requests in electronic form. Purchases paid with a Government-wide commercial purchase card are considered to be an electronic transaction for purposes of this rule, and therefore no additional electronic invoice submission is required.

 (c) *Data transmission.* A contractor must ensure that the data transmission method and format are through one of the following:

 (1) VA’s Electronic Invoice Presentment and Payment System. (See Web site at *http://www.fsc.va.gov/einvoice.asp*.)

 (2) Any system that conforms to the X12 electronic data interchange (EDI) formats established by the Accredited Standards Center (ASC) and chartered by the American National Standards Institute (ANSI). The X12 EDI Web site (*http://www.x12.org*) includes additional information on EDI 810 and 811 formats.

 (d) *Invoice requirements.* Invoices shall comply with FAR 32.905.

 (e) *Exceptions.* If, based on one of the circumstances below, the contracting officer directs that payment requests be made by mail, the contractor shall submit payment requests by mail through the United States Postal Service to the designated agency office. Submission of payment requests by mail may be required for:

 (1) Awards made to foreign vendors for work performed outside the United States;

 (2) Classified contracts or purchases when electronic submission and processing of payment requests could compromise the safeguarding of classified or privacy information;

 (3) Contracts awarded by contracting officers in the conduct of emergency operations, such as responses to national emergencies;

 (4) Solicitations or contracts in which the designated agency office is a VA entity other than the VA Financial Services Center in Austin, Texas; or

 (5) Solicitations or contracts in which the VA designated agency office does not have electronic invoicing capability as described above.

(End of Clause)

## 4.22 VAAR 852.236-71 SPECIFICATIONS AND DRAWINGS FOR CONSTRUCTION (JUL 2002)

 The clause entitled "Specifications and Drawings for Construction" in FAR 52.236-21 is supplemented as follows:

 (a) The contracting officer's interpretation of the drawings and specifications will be final, subject to the disputes clause.

 (b) Large scale drawings supersede small scale drawings.

 (c) Dimensions govern in all cases. Scaling of drawings may be done only for general location and general size of items.

 (d) Dimensions shown of existing work and all dimensions required for work that is to connect with existing work shall be verified by the contractor by actual measurement of the existing work. Any work at variance with that specified or shown in the drawings shall not be performed by the contractor until approved in writing by the contracting officer.

(End of Clause)

## 4.23 VAAR 852.236-72 PERFORMANCE OF WORK BY THE CONTRACTOR (JUL 2002)

 The clause entitled "Performance of Work by the Contractor" in FAR 52.236-1 is supplemented as follows:

 (a) Contract work accomplished on the site by laborers, mechanics, and foremen/forewomen on the contractor's payroll and under his/her direct supervision shall be included in establishing the percent of work to be performed by the contractor. Cost of material and equipment installed by such labor may be included. The work by the contractor's executive, supervisory and clerical forces shall be excluded in establishing compliance with the requirements of this clause.

 (b) The contractor shall submit, simultaneously with the schedule of costs required by the Payments Under Fixed-Price Construction Contracts clause of the contract, a statement designating the branch or branches of contract work to be performed with his/her forces. The approved schedule of costs will be used in determining the value of a branch or branches, or portions thereof, of the work for the purpose of this article.

 (c) If, during the progress of work hereunder, the contractor requests a change in the branch or branches of the work to be performed by his/her forces and the contracting officer determines it to be in the best interest of the Government, the contracting officer may, at his/her discretion, authorize a change in such branch or branches of said work. Nothing contained herein shall permit a reduction in the percentage of work to be performed by the contractor with his/her forces, it being expressly understood that this is a contract requirement without right or privilege of reduction.

 (d) In the event the contractor fails or refuses to meet the requirement of the FAR clause at 52.236-1, it is expressly agreed that the contract price will be reduced by 15 percent of the value of that portion of the percentage requirement that is accomplished by others. For the purpose of this clause, it is agreed that 15 percent is an acceptable estimate of the contractor's overhead and profit, or mark-up, on that portion of the work which the contractor fails or refuses to perform, with his/her own forces, in accordance with the FAR clause at 52.236-1.

(End of Clause)

## 4.24 VAAR 852.236-74 INSPECTION OF CONSTRUCTION (JUL 2002)

 The clause entitled "Inspection of Construction" in FAR 52.246-12 is supplemented as follows:

 (a) Inspection of materials and articles furnished under this contract will be made at the site by the resident engineer, unless otherwise provided for in the specifications.

 (b) Final inspection will not be made until the contract work is ready for beneficial use or occupancy. The contractor shall notify the contracting officer, through the resident engineer, fifteen (15) days prior to the date on which the work will be ready for final inspection.

(End of Clause)

## 4.25 VAAR 852.236-76 CORRESPONDENCE (APR 1984)

 All correspondence relative to this contract shall bear Specification Number, Project Number, Department of Veterans Affairs Contract Number, title of project and name of facility.

(End of Clause)

## 4.26 VAAR 852.236-77 REFERENCE TO "STANDARDS" (JUL 2002)

 Any materials, equipment, or workmanship specified by references to number, symbol, or title of any specific Federal, Industry or Government Agency Standard Specification shall comply with all applicable provisions of such standard specifications, except as limited to type, class or grade, or modified in contract specifications. Reference to "Standards" referred to in the contract specifications, except as modified, shall have full force and effect as though printed in detail in specifications.

(End of Clause)

## 4.27 VAAR 852.236-78 GOVERNMENT SUPERVISION (APR 1984)

 (a) The work will be under the direction of the Department of Veterans Affairs contracting officer, who may designate another VA employee to act as resident engineer at the construction site.

 (b) Except as provided below, the resident engineer's directions will not conflict with or change contract requirements.

 (c) Within the limits of any specific authority delegated by the contracting officer, the resident engineer may, by written direction, make changes in the work. The contractor shall be advised of the extent of such authority prior to execution of any work under the contract.

(End of Clause)

## 4.28 VAAR 852.236-79 DAILY REPORT OF WORKERS AND MATERIAL (APR 1984)

 The contractor shall furnish to the resident engineer each day a consolidated report for the preceding work day in which is shown the number of laborers, mechanics, foremen/forewomen and pieces of heavy equipment used or employed by the contractor and subcontractors. The report shall bear the name of the firm, the branch of work which they perform such as concrete, plastering, masonry, plumbing, sheet metal work, etc. The report shall give a breakdown of employees by crafts, location where employed, and work performed. The report shall also list materials delivered to the site on the date covered by the report.

(End of Clause)

## 4.29 VAAR 852.236-80 SUBCONTRACTS AND WORK COORDINATION (APR 1984)

 (a) Nothing contained in this contract shall be construed as creating any contractual relationship between any subcontractor and the Government. Divisions or sections of specifications are not intended to control the contractor in dividing work among subcontractors, or to limit work performed by any trade.

 (b) The contractor shall be responsible to the Government for acts and omissions of his/her own employees, and of the subcontractors and their employees. The contractor shall also be responsible for coordination of the work of the trades, subcontractors, and material suppliers.

 (c) The Government or its representatives will not undertake to settle any differences between the contractor and subcontractors or between subcontractors.

 (d) The Government reserves the right to refuse to permit employment on the work or require dismissal from the work of any subcontractor who, by reason of previous unsatisfactory work on Department of Veterans Affairs projects or for any other reason, is considered by the contracting officer to be incompetent or otherwise objectionable.

(End of Clause)

## 4.30 VAAR 852.236-82 PAYMENTS UNDER FIXED-PRICE CONSTRUCTION CONTRACTS (WITHOUT NAS) (APR 1984)

 (a) Retainage:

 (1) The contracting officer may retain funds:

 (i) Where performance under the contract has been determined to be deficient or the contractor has performed in an unsatisfactory manner in the past; or

 (ii) As the contract nears completion, to ensure that deficiencies will be corrected and that completion is timely.

 (2) Examples of deficient performance justifying a retention of funds include, but are not restricted to, the following:

 (i) Unsatisfactory progress as determined by the contracting officer;

 (ii) Failure to meet schedule in Schedule of Work Progress;

 (iii) Failure to present submittals in a timely manner; or

 (iv) Failure to comply in good faith with approved subcontracting plans, certifications, or contract requirements.

 (3) Any level of retention shall not exceed 10 percent either where there is determined to be unsatisfactory performance, or when the retainage is to ensure satisfactory completion. Retained amounts shall be paid promptly upon completion of all contract requirements, but nothing contained in this subparagraph shall be construed as limiting the contracting officer's right to withhold funds under other provisions of the contract or in accordance with the general law and regulations regarding the administration of Government contracts.

 (b) The contractor shall submit a schedule of cost to the contracting officer for approval within 30 calendar days after date of receipt of notice to proceed. Such schedule will be signed and submitted in triplicate. The approved cost schedule will be one of the bases for determining progress payments to the contractor for work completed. This schedule shall show cost by the branches of work for each building or unit of the contract, as instructed by the resident engineer.

 (1) The branches shall be subdivided into as many sub-branches as are necessary to cover all component parts of the contract work.

 (2) Costs as shown on this schedule must be true costs and, should the resident engineer so desire, he/she may require the contractor to submit the original estimate sheets or other information to substantiate the detailed makeup of the schedule.

 (3) The sum of the sub-branches, as applied to each branch, shall equal the total cost of such branch. The total cost of all branches shall equal the contract price.

 (4) Insurance and similar items shall be prorated and included in the cost of each branch of the work.

 (5) The cost schedule shall include separate cost information for the systems listed in the table in this paragraph (b)(5). The percentages listed below are proportions of the cost listed in the contractor's cost schedule and identify, for payment purposes, the value of the work to adjust, correct and test systems after the material has been installed. Payment of the listed percentages will be made only after the contractor has demonstrated that each of the systems is substantially complete and operates as required by the contract.

VALUE OF ADJUSTING, CORRECTING, AND TESTING SYSTEM

|  |  |
| --- | --- |
| **System** | **Percent** |
| Pneumatic tube system | 10 |
| Incinerators (medical waste and trash) | 5 |
| Sewage treatment plant equipment | 5 |
| Water treatment plant equipment | 5 |
| Washers (dish, cage, glass, etc.) | 5 |
| Sterilizing equipment | 5 |
| Water distilling equipment | 5 |
| Prefab temperature rooms (cold, constant temperature) | 5 |
| Entire air-conditioning system (Specified under 600 Sections) | 5 |
| Entire boiler plant system (Specified under 700 Sections) | 5 |
| General supply conveyors | 10 |
| Food service conveyors | 10 |
| Pneumatic soiled linen and trash system | 10 |
| Elevators and dumbwaiters | 10 |
| Materials transport system | 10 |
| Engine-generator system | 5 |
| Primary switchgear | 5 |
| Secondary switchgear | 5 |
| Fire alarm system | 5 |
| Nurse call system | 5 |
| Intercom system | 5 |
| Radio system | 5 |
| TV (entertainment) system | 5 |

 (c) In addition to this cost schedule, the contractor shall submit such unit costs as may be specifically requested. The unit costs shall be those used by the contractor in preparing his/her bid and will not be binding as pertaining to any contract changes.

 (d) The contracting officer will consider for monthly progress payments material and/or equipment procured by the contractor and stored on the construction site, as space is available, or at a local approved location off the site, under such terms and conditions as such officer approves, including but not limited to the following:

 (1) The material or equipment is in accordance with the contract requirements and/or approved samples and shop drawings.

 (2) Only those materials and/or equipment as are approved by the resident engineer for storage will be included.

 (3) Such materials and/or equipment will be stored separately and will be readily available for inspection and inventory by the resident engineer.

 (4) Such materials and/or equipment will be protected against weather, theft and other hazards and will not be subjected to deterioration.

 (5) All of the other terms, provisions, conditions and covenants contained in the contract shall be and remain in full force and effect as therein provided.

 (6) A supplemental agreement will be executed between the Government and the contractor with the consent of the contractor's surety for off-site storage.

 (e) The contractor, prior to receiving a progress or final payment under this contract, shall submit to the contracting officer a certification that the contractor has made payment from proceeds of prior payments, or that timely payment will be made from the proceeds of the progress or final payment then due, to subcontractors and suppliers in accordance with the contractual arrangements with them.

 (f) The Government reserves the right to withhold payment until samples, shop drawings, engineer's certificates, additional bonds, payrolls, weekly statements of compliance, proof of title, nondiscrimination compliance reports, or any other things required by this contract, have been submitted to the satisfaction of the contracting officer.

(End of Clause)

## 4.31 VAAR 852.236-84 SCHEDULE OF WORK PROGRESS (NOV 1984)

 (a) The contractor shall submit with the schedule of costs, a progress schedule that indicates the anticipated installation of work versus the elapsed contract time, for the approval of the contracting officer. The progress schedule time shall be represented in the form of a bar graph with the contract time plotted along the horizontal axis. The starting date of the schedule shall be the date the contractor receives the "Notice to Proceed." The ending date shall be the original contract completion date. At a minimum, both dates shall be indicated on the progress schedule. The specific item of work, i.e., "Excavation", "Floor Tile", "Finish Carpentry", etc., should be plotted along the vertical axis and indicated by a line or bar at which time(s) during the contract this work is scheduled to take place. The schedule shall be submitted in triplicate and signed by the contractor.

 (b) The actual percent completion will be based on the value of installed work divided by the current contract amount. The actual completion percentage will be indicated on the monthly progress report.

 (c) The progress schedule will be revised when individual or cumulative time extensions of 15 calendar days or more are granted for any reason. The revised schedule should indicate the new contract completion date and should reflect any changes to the installation time(s) of the items of work affected.

 (d) The revised progress schedule will be used for reporting future scheduled percentage completion.

(End of Clause)

## 4.32 VAAR 852.236-85 SUPPLEMENTARY LABOR STANDARDS PROVISIONS (APR 1984)

 (a) The wage determination decision of the Secretary of Labor is set forth in section GR, General Requirements, of this contract. It is the result of a study of wage conditions in the locality and establishes the minimum hourly rates of wages and fringe benefits for the described classes of labor in accordance with applicable law. No increase in the contract price will be allowed or authorized because of payment of wage rates in excess of those listed.

 (b) The contractor shall submit the required copies of payrolls to the contracting officer through the resident engineer or engineer officer, when acting in that capacity. Department of Labor Form WH- 347, Payroll, available from the Superintendent of Documents, Government Printing Office, Washington, DC 20402, may be used for this purpose. If, however, the contractor or subcontractor elects to use an individually composed payroll form, it shall contain the same information shown on Form WH-347, and in addition be accompanied by Department of Labor Form WH-348, Statement of Compliance, or any other form containing the exact wording of this form.

(End of Clause)

## 4.33 VAAR 852.236-86 WORKER'S COMPENSATION (JAN 2008)

 Public Law 107-217 (40 U.S.C. 3172) authorizes the constituted authority of States to apply their workers compensation laws to all lands and premises owned or held by the United States.

(End of Clause)

## 4.34 VAAR 852.236-88 CONTRACT CHANGES--SUPPLEMENT (JUL 2002)

 The clauses entitled “Changes” in FAR 52.243-4 and “Differing Site Conditions” in FAR 52.236-2 are supplemented as follows:

 (a) Paragraphs (a)(1) through (a)(4) apply to proposed contract changes costing over $500,000.

 (1) When requested by the contracting officer, the contractor shall submit proposals for changes in work to the resident engineer. Proposals, to be submitted as expeditiously as possible but within 30 calendar days after receipt of request, shall be in legible form, original and two copies, with an itemized breakdown that will include material, quantities, unit prices, labor costs (separated into trades), construction equipment, etc. (Labor costs are to be identified with specific material placed or operation performed.) The contractor must obtain and furnish with a proposal an itemized breakdown as described above, signed by each subcontractor participating in the change regardless of tier. When certified cost or pricing data are required under FAR Subpart 15.403, the cost or pricing data shall be submitted in accordance with FAR 15.403-5.

 (2) When the necessity to proceed with a change does not allow sufficient time to negotiate a modification or because of failure to reach an agreement, the contracting officer may issue a change order instructing the contractor to proceed on the basis of a tentative price based on the best estimate available at the time, with the firm price to be determined later. Furthermore, when the change order is issued, the contractor shall submit a proposal, which includes the information required by paragraph (a)(1), for cost of changes in work within 30 calendar days.

 (3) The contracting officer will consider issuing a settlement by determination to the contract if the contractor's proposal required by paragraphs (a)(1) or (a)(2) of this clause is not received within 30 calendar days or if agreement has not been reached.

 (4) Bond premium adjustment, consequent upon changes ordered, will be made as elsewhere specified at the time of final settlement under the contract and will not be included in the individual change.

 (b) Paragraphs (b)(1) through (b)(11) apply to proposed contract changes costing $500,000 or less:

 (1) When requested by the contracting officer, the contractor shall submit proposals for changes in work to the resident engineer. Proposals, to be submitted as expeditiously as possible but within 30 calendar days after receipt of request, shall be in legible form, original and two copies, with an itemized breakdown that will include material, quantities, unit prices, labor costs (separated into trades), construction equipment, etc. (Labor costs are to be identified with specific material placed or operation performed.) The contractor must obtain and furnish with a proposal an itemized breakdown as described above, signed by each subcontractor participating in the change regardless of tier. When certified cost or pricing data or information other than cost or pricing data are required under FAR 15.403, the data shall be submitted in accordance with FAR 15.403-5. No itemized breakdown will be required for proposals amounting to less than $1,000.

 (2) When the necessity to proceed with a change does not allow sufficient time to negotiate a modification or because of failure to reach an agreement, the contracting officer may issue a change order instructing the contractor to proceed on the basis of a tentative price based on the best estimate available at the time, with the firm price to be determined later. Furthermore, when the change order is issued, the contractor shall submit within 30 calendar days, a proposal that includes the information required by paragraph (b)(1) for the cost of the changes in work.

 (3) The contracting officer will consider issuing a settlement by determination to the contract if the contractor's proposal required by paragraphs (b)(1) or (b)(2) of this clause is not received within 30 calendar days, or if agreement has not been reached.

 (4) Allowances not to exceed 10 percent each for overhead and profit for the party performing the work will be based on the value of labor, material, and use of construction equipment required to accomplish the change. As the value of the change increases, a declining scale will be used in negotiating the percentage of overhead and profit. Allowable percentages on changes will not exceed the following: 10 percent overhead and 10 percent profit on the first $20,000; 7-1/2 percent overhead and 7-1/2 percent profit on the next $30,000; 5 percent overhead and 5 percent profit on balance over $50,000. Profit shall be computed by multiplying the profit percentage by the sum of the direct costs and computed overhead costs.

 (5) The prime contractor's or upper-tier subcontractor's fee on work performed by lower-tier subcontractors will be based on the net increased cost to the prime contractor or upper-tier subcontractor, as applicable. Allowable fee on changes will not exceed the following: 10 percent fee on the first $20,000; 7-1/2 percent fee on the next $30,000; and 5 percent fee on balance over $50,000.

 (6) Not more than four percentages, none of which exceed the percentages shown above, will be allowed regardless of the number of tiers of subcontractors.

 (7) Where the contractor's or subcontractor's portion of a change involves credit items, such items must be deducted prior to adding overhead and profit for the party performing the work. The contractor's fee is limited to the net increase to contractor of subcontractors' portions cost computed in accordance herewith.

 (8) Where a change involves credit items only, a proper measure of the amount of downward adjustment in the contract price is the reasonable cost to the contractor if he/she had performed the deleted work. A reasonable allowance for overhead and profit are properly includable as part of the downward adjustment for a deductive change. The amount of such allowance is subject to negotiation.

 (9) Cost of Federal Old Age Benefit (Social Security) tax and of Worker's Compensation and Public Liability insurance appertaining to changes are allowable. While no percentage will be allowed thereon for overhead or profit, prime contractor's fee will be allowed on such items in subcontractors' proposals.

 (10) Overhead and contractor's fee percentages shall be considered to include insurance other than mentioned herein, field and office supervisors and assistants, security police, use of small tools, incidental job burdens, and general home office expenses and no separate allowance will be made therefore. Assistants to office supervisors include all clerical, stenographic and general office help. Incidental job burdens include, but are not necessarily limited to, office equipment and supplies, temporary toilets, telephone and conformance to OSHA requirements. Items such as, but not necessarily limited to, review and coordination, estimating and expediting relative to contract changes are associated with field and office supervision and are considered to be included in the contractor's overhead and/or fee percentage.

 (11) Bond premium adjustment, consequent upon changes ordered, will be made as elsewhere specified at the time of final settlement under the contract and will not be included in the individual change.

(End of Clause)

## 4.35 VAAR 852.236-89 BUY AMERICAN ACT (JAN 2008)

 (a) Reference is made to the clause entitled "Buy American Act--Construction Materials," FAR 52.225-9.

 (b) Notwithstanding a bidder's right to offer identifiable foreign construction material in its bid pursuant to FAR 52.225-9, VA does not anticipate accepting an offer that includes foreign construction material.

 (c) If a bidder chooses to submit a bid that includes foreign construction material, that bidder must provide a listing of the specific foreign construction material he/she intends to use and a price for said material. Bidders must include bid prices for comparable domestic construction material. If VA determines not to accept foreign construction material and no comparable domestic construction material is provided, the entire bid will be rejected.

 (d) Any foreign construction material proposed after award will be rejected unless the bidder proves to VA's satisfaction: (1) it was impossible to request the exemption prior to award, and (2) said domestic construction material is no longer available, or (3) where the price has escalated so dramatically after the contract has been awarded that it would be unconscionable to require performance at that price. The determinations required by (1), (2), and (3) of this paragraph shall be made in accordance with Subpart 825.2 and FAR 25.2.

 (e) By signing this bid, the bidder declares that all articles, materials and supplies for use on the project shall be domestic unless specifically set forth on the Bid Form or addendum thereto.

(End of Clause)

## 4.36 VAAR 852.236-91 SPECIAL NOTES (JUL 2002)

 (a) Signing of the bid shall be deemed to be a representation by the bidder that:

 (1) Bidder is a construction contractor who owns, operates, or maintains a place of business, regularly engaged in construction, alteration, or repair of buildings, structures, and communications facilities, or other engineering projects, including furnishing and installing of necessary equipment; or

 (2) If newly entering into a construction activity, bidder has made all necessary arrangements for personnel, construction equipment, and required licenses to perform construction work; and

 (3) Upon request, prior to award, bidder will promptly furnish to the Government a statement of facts in detail as to bidder's previous experience (including recent and current contracts), organization (including company officers), technical qualifications, financial resources and facilities available to perform the contemplated work.

 (b) Unless otherwise provided in this contract, where the use of optional materials or construction is permitted, the same standard of workmanship, fabrication and installation shall be required irrespective of which option is selected. The contractor shall make any change or adjustment in connecting work or otherwise necessitated by the use of such optional material or construction, without additional cost to the Government.

 (c) When approval is given for a system component having functional or physical characteristics different from those indicated or specified, it is the responsibility of the contractor to furnish and install related components with characteristics and capacities compatible with the approved substitute component as required for systems to function as noted on drawings and specifications. There shall be no additional cost to the Government.

 (d) In some instances it may have been impracticable to detail all items in specifications or on drawings because of variances in manufacturers' methods of achieving specified results. In such instances the contractor will be required to furnish all labor, materials, drawings, services and connections necessary to produce systems or equipment which are completely installed, functional, and ready for operation by facility personnel in accordance with their intended use.

 (e) Claims by the contractor for delay attributed to unusually severe weather must be supported by climatological data covering the period and the same period for the 10 preceding years. When the weather in question exceeds in intensity or frequency the 10-year average, the excess experienced shall be considered "unusually severe." Comparison shall be on a monthly basis. Whether or not unusually severe weather in fact delays the work will depend upon the effect of weather on the branches of work being performed during the time under consideration.

(End of Clause)

## 4.37 VAAR 852.246-74 SPECIAL WARRANTIES (JAN 2008)

 The clause entitled "Warranty of Construction" in FAR 52.246-21 is supplemented as follows:

 Any special warranties that may be required under the contract shall be subject to the elections set forth in the FAR clause at 52.246-21, Warranty of Construction, unless otherwise provided for in such special warranties.

(End of Clause)

# SECTION D – CONTRACT DOCUMENTS, EXHIBITS, OR ATTACHMENTS

ATTACHMENT 1 – CONSTRUCTION WAGE RATES

ATTACHMENT 2 – PAST PERFORMANCE QUESTIONNAIRE

ATTACHMENT 3 – CONTRACTOR PRODUCTION REPORT

ATTACHMENT 4 – CONTRACTOR QUALITY CONTROL REPORT

ATTACHMENT 5 – CONTRACT DISCREPANCY REPORT

ATTACHMENT 6 – ILLUSTRATIONS AND DRAWINGS

**4.38 ATTACHMENT 1 – CONSTRUCTION WAGE RATES**

General Decision Number: ME170025 06/16/2017 ME25

Superseded General Decision Number: ME20160025

State: Maine

Construction Type: Building

County: Kennebec County in Maine.

BUILDING CONSTRUCTION PROJECTS (does not include single family

homes or apartments up to and including 4 stories).

Note: Under Executive Order (EO) 13658, an hourly minimum wage

of $10.20 for calendar year 2017 applies to all contracts

subject to the Davis-Bacon Act for which the contract is

awarded (and any solicitation was issued) on or after January

1, 2015. If this contract is covered by the EO, the contractor

must pay all workers in any classification listed on this wage

determination at least $10.20 (or the applicable wage rate

listed on this wage determination, if it is higher) for all

hours spent performing on the contract in calendar year 2017.

The EO minimum wage rate will be adjusted annually. Additional

information on contractor requirements and worker protections

under the EO is available at www.dol.gov/whd/govcontracts.

Modification Number Publication Date

 0 01/06/2017

 1 01/20/2017

 2 06/02/2017

 3 06/16/2017

\* ELEC1253-007 06/01/2017

 Rates Fringes

ELECTRICIAN

 Electrician (Industrial

 Work Only)..................$ 28.80 14.91

 Teledata Technician.........$ 23.56 13.51

----------------------------------------------------------------

 ELEV0004-004 01/01/2016

 Rates Fringes

ELEVATOR MECHANIC................$ 54.53 29.985

 a. PAID HOLIDAYS: New Year's Day, Memorial Day, Independence

 Day, Labor Day, Veterans' Day, Thanksgiving Day, Christmas

 Day and the Friday after Thanksgiving.

 b. VACATION: Employer contributes 8% of basic hourly rate for

 5 years or more of service; 6% of basic hourly rate for 6

 months to 5 years of service as vacation pay credit.

----------------------------------------------------------------

 IRON0007-020 03/16/2016

 Rates Fringes

IRONWORKER, STRUCTURAL...........$ 23.68 21.14

----------------------------------------------------------------

 PLUM0716-004 08/15/2016

 Rates Fringes

PIPEFITTER (Excluding HVAC

Pipe Installation)...............$ 28.00 15.71

----------------------------------------------------------------

 SUME2011-020 03/23/2011

 Rates Fringes

BRICKLAYER.......................$ 26.03 5.14

CARPENTER, Includes

Acoustical Ceiling

Installation, and Form Work......$ 16.42 6.07

CEMENT MASON/CONCRETE FINISHER...$ 13.07 2.54

DRYWALL FINISHER/TAPER...........$ 19.78 0.00

DRYWALL HANGER...................$ 17.80 1.74

ELECTRICIAN (Low Voltage

Wiring and Installation of

Alarms)..........................$ 17.00 0.78

ELECTRICIAN......................$ 22.25 7.19

FLOOR LAYER: Vinyl Flooring.....$ 16.38 0.00

HVAC MECHANIC: HVAC UNIT

INSTALLATION.....................$ 28.81 1.38

INSULATOR - BATT.................$ 13.49 3.52

IRONWORKER, REINFORCING..........$ 12.67 2.29

LABORER: Landscape..............$ 17.00 0.65

LABORER: Mortar Mixer...........$ 16.93 4.61

LABORER: Common or General,

Including brick mason

tending, cement mason tending

and formstripping................$ 12.95 2.48

OPERATOR: Backhoe...............$ 14.62 3.23

OPERATOR: Bulldozer.............$ 22.18 11.18

OPERATOR: Crane.................$ 18.06 4.63

OPERATOR: Excavator.............$ 17.18 4.46

OPERATOR: Loader................$ 14.90 0.93

OPERATOR: Roller................$ 12.65 0.00

PAINTER: Brush and Roller.......$ 18.38 6.98

PLUMBER, Includes HVAC Pipe

Installation.....................$ 21.94 2.81

ROOFER, Includes Installation

of Metal Roofs...................$ 16.69 1.91

SHEET METAL WORKER, Includes

HVAC Duct Installation...........$ 15.88 3.59

SPRINKLER FITTER (Fire

Sprinklers)......................$ 15.00 0.00

TRUCK DRIVER: Dump Truck........$ 15.00 2.71

----------------------------------------------------------------

WELDERS - Receive rate prescribed for craft performing

operation to which welding is incidental.

================================================================

Note: Executive Order (EO) 13706, Establishing Paid Sick Leave

for Federal Contractors applies to all contracts subject to the

Davis-Bacon Act for which the contract is awarded (and any

solicitation was issued) on or after January 1, 2017. If this

contract is covered by the EO, the contractor must provide

employees with 1 hour of paid sick leave for every 30 hours

they work, up to 56 hours of paid sick leave each year.

Employees must be permitted to use paid sick leave for their

own illness, injury or other health-related needs, including

preventive care; to assist a family member (or person who is

like family to the employee) who is ill, injured, or has other

health-related needs, including preventive care; or for reasons

resulting from, or to assist a family member (or person who is

like family to the employee) who is a victim of, domestic

violence, sexual assault, or stalking. Additional information

on contractor requirements and worker protections under the EO

is available at www.dol.gov/whd/govcontracts.

Unlisted classifications needed for work not included within

the scope of the classifications listed may be added after

award only as provided in the labor standards contract clauses

(29CFR 5.5 (a) (1) (ii)).

----------------------------------------------------------------

The body of each wage determination lists the classification

and wage rates that have been found to be prevailing for the

cited type(s) of construction in the area covered by the wage

determination. The classifications are listed in alphabetical

order of "identifiers" that indicate whether the particular

rate is a union rate (current union negotiated rate for local),

a survey rate (weighted average rate) or a union average rate

(weighted union average rate).

Union Rate Identifiers

A four letter classification abbreviation identifier enclosed

in dotted lines beginning with characters other than "SU" or

"UAVG" denotes that the union classification and rate were

prevailing for that classification in the survey. Example:

PLUM0198-005 07/01/2014. PLUM is an abbreviation identifier of

the union which prevailed in the survey for this

classification, which in this example would be Plumbers. 0198

indicates the local union number or district council number

where applicable, i.e., Plumbers Local 0198. The next number,

005 in the example, is an internal number used in processing

the wage determination. 07/01/2014 is the effective date of the

most current negotiated rate, which in this example is July 1,

2014.

Union prevailing wage rates are updated to reflect all rate

changes in the collective bargaining agreement (CBA) governing

this classification and rate.

Survey Rate Identifiers

Classifications listed under the "SU" identifier indicate that

no one rate prevailed for this classification in the survey and

the published rate is derived by computing a weighted average

rate based on all the rates reported in the survey for that

classification. As this weighted average rate includes all

rates reported in the survey, it may include both union and

non-union rates. Example: SULA2012-007 5/13/2014. SU indicates

the rates are survey rates based on a weighted average

calculation of rates and are not majority rates. LA indicates

the State of Louisiana. 2012 is the year of survey on which

these classifications and rates are based. The next number, 007

in the example, is an internal number used in producing the

wage determination. 5/13/2014 indicates the survey completion

date for the classifications and rates under that identifier.

Survey wage rates are not updated and remain in effect until a

new survey is conducted.

Union Average Rate Identifiers

Classification(s) listed under the UAVG identifier indicate

that no single majority rate prevailed for those

classifications; however, 100% of the data reported for the

classifications was union data. EXAMPLE: UAVG-OH-0010

08/29/2014. UAVG indicates that the rate is a weighted union

average rate. OH indicates the state. The next number, 0010 in

the example, is an internal number used in producing the wage

determination. 08/29/2014 indicates the survey completion date

for the classifications and rates under that identifier.

A UAVG rate will be updated once a year, usually in January of

each year, to reflect a weighted average of the current

negotiated/CBA rate of the union locals from which the rate is

based.

----------------------------------------------------------------

 WAGE DETERMINATION APPEALS PROCESS

1.) Has there been an initial decision in the matter? This can

be:

\* an existing published wage determination

\* a survey underlying a wage determination

\* a Wage and Hour Division letter setting forth a position on

 a wage determination matter

\* a conformance (additional classification and rate) ruling

On survey related matters, initial contact, including requests

for summaries of surveys, should be with the Wage and Hour

Regional Office for the area in which the survey was conducted

because those Regional Offices have responsibility for the

Davis-Bacon survey program. If the response from this initial

contact is not satisfactory, then the process described in 2.)

and 3.) should be followed.

With regard to any other matter not yet ripe for the formal

process described here, initial contact should be with the

Branch of Construction Wage Determinations. Write to:

 Branch of Construction Wage Determinations

 Wage and Hour Division

 U.S. Department of Labor

 200 Constitution Avenue, N.W.

 Washington, DC 20210

2.) If the answer to the question in 1.) is yes, then an

interested party (those affected by the action) can request

review and reconsideration from the Wage and Hour Administrator

(See 29 CFR Part 1.8 and 29 CFR Part 7). Write to:

 Wage and Hour Administrator

 U.S. Department of Labor

 200 Constitution Avenue, N.W.

 Washington, DC 20210

The request should be accompanied by a full statement of the

interested party's position and by any information (wage

payment data, project description, area practice material,

etc.) that the requestor considers relevant to the issue.

3.) If the decision of the Administrator is not favorable, an

interested party may appeal directly to the Administrative

Review Board (formerly the Wage Appeals Board). Write to:

 Administrative Review Board

 U.S. Department of Labor

 200 Constitution Avenue, N.W.

 Washington, DC 20210

4.) All decisions by the Administrative Review Board are final.

================================================================

 END OF GENERAL DECISION

**4.39 ATTACHMENT 2 – PAST PERFORMANCE QUESTIONNAIRE**

**INSTRUCTIONS**: **Offerors must identify previous federal, state, and local government and private contracts that they have completed and that are similar to the contract being evaluated. List at least three (3), but no more than five (5) contracts for evaluation limited to the last five (3) years. (One contract reference per form; Form may be duplicated)**

**NOTE: If you have performed any National Cemetery Administration contracts, list them first.**

**Contractor (you) Information:**

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Telephone Number: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

E-mail: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Contract Information:**

Name of company/agency you provided service for: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Contract Number: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Type of Contract: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Contract Dollar Value: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date of Award: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Status: Completed, Yes\_\_\_\_ No\_\_\_\_ If not completed, projected completion date\_\_\_\_\_\_\_\_\_\_\_\_
If not completed, why?\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Were you the Prime? \_\_\_\_\_\_\_\_ were you the Sub? \_\_\_\_\_\_\_

**Point of Contact Information for the company/agency you serviced:**

Name of the Contract Person & their position: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Telephone Number: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

E-mail: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Description of Supply/Service(s) provided, location & relevancy of work:**

**Complexity of Product/Service, if any:**

**Percentage of Work completed by your company/by subcontractor:**

If you did less than 100% please explain the tasks you performed.

 **(End of Section)**

|  |  |  |
| --- | --- | --- |
| **4.40 ATTACHMENT 3 – CONTRACTOR PRODUCTION REPORT**CONTRACTOR PRODUCTION REPORT(ATTACH ADDITIONAL SHEETS IF NECESSARY) | DATE |  |
| CONTRACT NO: | TITLE AND LOCATION |  | REPORT NO |  |
|  |  |
| CONTRACTOR |  | SUPERINTENDENT |  |
|  |  |
| AM WEATHER |  | PM WEATHER |  | MAX TEMP (F) | MIN TEMP (F) |
|  |  |  |  |
| WORK PERFORMED TODAY |
| Schedule Activity No. | WORK LOCATION AND DESCRIPTION | EMPLOYER | NUMBER  | TRADE | HRS |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  CODE COMPLIANTIs the installation of equipment and material code complaint?  |  |  |  |  |
|  | If it is code compliant what specific requirement (section, number) does it meet?  |  |  |  |  |
|  |  |  |  |  |  |
| JOB**SAFETY** | WAS A JOB SAFETY MEETING HELD THIS DATE?(If YES attach copy of the meeting minutes) | [ ]  YES | [ ]  NO | TOTAL WORK HOURS ON JOB SITE,THIS DATE, INCL CON'T SHEETS |  |
| WERE THERE ANY LOST TIME ACCIDENTS THIS DATE?(If YES attach copy of completed OSHA report) | [ ]  YES | [ ]  NO | CUMULATIVE TOTAL OF WORKHOURS FROM PREVIOUS REPORT |  |
| WAS CRANE/MANLIFT/TRENCHING/SCAFFOLD/HV ELEC/HIGH WORK/ HAZMAT WORK DONE?(If YES attach statement or checklist showing inspection performed.) | [ ]  YES | [ ]  NO |
| TOTAL WORK HOURS FROM START OF CONSTRUCTION |  |
| WAS HAZARDOUS MATERIAL/WASTE RELEASED INTO THE ENVIRONMENT?(If YES attach description of incident and proposed action.) | [ ]  YES | [ ]  NO |
| ScheduleActivity No. | LIST SAFETY ACTIONS TAKEN TODAY/SAFETY INSPECTIONS CONDUCTED | [ ]  | SAFETY REQUIREMENTS HAVE BEEN MET. |
|  |  |
|  |  |
|  |  |
| EQUIPMENT/MATERIAL RECEIVED TODAY TO BE INCORPORATED IN JOB (INDICATE SCHEDULE ACTIVITY NUMBER) |
| ScheduleActivity No. | Submittal # | Description of Equipment/Material Received |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| CONSTRUCTION AND PLANT EQUIPMENT ON JOB SITE TODAY. INDICATE HOURS USED AND SCHEDULE ACTIVITY NUMBER. |
| ScheduleActivity No. | Owner | Description of Construction Equipment Used Today (incl Make and Model) | Hours Used |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| ScheduleActivity No. | REMARKS |
|  |  |
|  |  |
|  |  |
|  |  |
| By signing this report the signee is in agreement that the installations and information in this report are accurate, have been inspected and are compliant with the contract documents, specific code requirements and SpecificationSection 01-40-01 1.5 |
|  | CONTRACTOR/SUPERINTENDENT | DATE |  |

|  |  |  |
| --- | --- | --- |
|  **4.41 ATTACHMENT 4 – CONTRACTOR QUALITY CONTROL REPORT**(ATTACH ADDITIONAL SHEETS IF NECESSARY) | DATE |  |
| REPORT NO  |  |
| PHASE | CONTRACT NO |  | CONTRACT TITLE |  |
| **PREPARATORY** | WAS PREPARATORY PHASE WORK PREFORMED TODAY? | YES [ ]  | NO [ ]  |  |
| IF YES, FILL OUT AND ATTACH SUPPLEMENTAL PREPARATORY PHASE CHECKLIST. |
| ScheduleActivity No. | Definable Feature of Work | Index # |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| **INITIAL** | WAS INITIAL PHASE WORK PREFORMED TODAY? | YES [ ]  | NO [ ]  |  |
| IF YES, FILL OUT AND ATTACH SUPPLEMENTAL INITIAL PHASE CHECKLIST. |
| ScheduleActivity No. | Definable Feature of Work | Index # |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| **FOLLOW-UP** | WORK COMPLIES WITH CONTRACT AS APPROVED DURING INITIAL PHASE? | YES [ ]  | NO [ ]  |  |
| WORK COMPLIES WITH SAFETY REQUIREMENTS? | YES [ ]  | NO [ ]  |
| ScheduleActivity No. | Description of Work, Testing Performed & By Whom, Definable Feature of Work, SpecificationSection, Location and List of Personnel Present |
|
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
| REWORK ITEMS IDENTIFIED TODAY (NOT CORRECTED BY CLOSE OF BUSINESS) | REWORK ITEMS CORRECTED TODAY (FROM REWORK ITEMS LIST) |
| ScheduleActivity No. | Description | ScheduleActivity No. | Description |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  REMARKS (Also Explain Any Follow-Up Phase Checklist Item From Above That Was Answered "NO"), Manuf. Rep On-Site, etc. |
| ScheduleActivity No. | Description |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|   On behalf of the contractor, I certify that this report is complete and correct and  equipment and material used and work performed during this reporting period is in compliance with the contract drawings and specifications to the best of my knowledge  except as noted in this report. AUTHORIZED QC MANAGER AT SITE DATE |
| GOVERNMENT QUALITY ASSURANCE REPORT | DATE |  |
| QUALITY ASSURANCE REPRESENTATIVE'S REMARKS AND/OR EXCEPTIONS TO THE REPORT |
| ScheduleActivity No. | Description |
|  |  |
|  |  |
|  |  |
|  |  |
|  |
|  | GOVERNMENT QUALITY ASSURANCE MANAGER | DATE |
| ATTACHMENT – E CONTRACTOR QUALITY CONTROL REPORT(ATTACH ADDITIONAL SHEETS IF NECESSARY) | DATE |  |
|  | REPORT NO  |  |
| PHASE | CONTRACT NO |  | CONTRACT TITLE |  |
| **PREPARATORY** | WAS PREPARATORY PHASE WORK PREFORMED TODAY? | YES [ ]  | NO [ ]  |  |
| IF YES, FILL OUT AND ATTACH SUPPLEMENTAL PREPARATORY PHASE CHECKLIST. |
| ScheduleActivity No. | Definable Feature of Work | Index # |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| **INITIAL** | WAS INITIAL PHASE WORK PREFORMED TODAY? | YES [ ]  | NO [ ]  |  |
| IF YES, FILL OUT AND ATTACH SUPPLEMENTAL INITIAL PHASE CHECKLIST. |
| ScheduleActivity No. | Definable Feature of Work | Index # |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| **FOLLOW-UP** | WORK COMPLIES WITH CONTRACT AS APPROVED DURING INITIAL PHASE? | YES [ ]  | NO [ ]  |  |
| WORK COMPLIES WITH SAFETY REQUIREMENTS? | YES [ ]  | NO [ ]  |
| ScheduleActivity No. | Description of Work, Testing Performed & By Whom, Definable Feature of Work, SpecificationSection, Location and List of Personnel Present |
|
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
| REWORK ITEMS IDENTIFIED TODAY (NOT CORRECTED BY CLOSE OF BUSINESS) | REWORK ITEMS CORRECTED TODAY (FROM REWORK ITEMS LIST) |
| ScheduleActivity No. | Description | ScheduleActivity No. | Description |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  REMARKS (Also Explain Any Follow-Up Phase Checklist Item From Above That Was Answered "NO"), Manuf. Rep On-Site, etc. |
| ScheduleActivity No. | Description |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|   On behalf of the contractor, I certify that this report is complete and correct and  equipment and material used and work performed during this reporting period is in compliance with the contract drawings and specifications to the best of my knowledge  except as noted in this report. AUTHORIZED QC MANAGER AT SITE DATE |
| GOVERNMENT QUALITY ASSURANCE REPORT | DATE |  |
| QUALITY ASSURANCE REPRESENTATIVE'S REMARKS AND/OR EXCEPTIONS TO THE REPORT |
| ScheduleActivity No. | Description |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |
|  | GOVERNMENT QUALITY ASSURANCE MANAGER | DATE |

|  |
| --- |
| 4.42 ATTACHMENT 5 – CONTRACT DISCREPANCY REPORT**CONTRACT DISCREPANCY REPORT** |
| Contract Number: | Report No. for this Discrepancy: |
| To: (Contractor/Manager’s Name) | From: (Name of COR) |
| 5. Dates |
| 5a. Prepared:  | 5b. Returned by Contractor: | 5c. Action Complete: |
| Discrepancy or Problem: (Describe in detail. Include reference to PWS Directive; attach additional sheet if necessary.)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Signature of Contracting Officer or COR: |
| 8a. To: (Contracting Officer and/or COR) | 8b. From: (Contractor) |
| 9. Contractor Response as to Cause, Corrective Action and Actions to Prevent Recurrence: (attach additional sheet if necessary.)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| 10a. Signature of Contractor Representative: | 10b. Date: |
| 11. Government Evaluation: (Acceptance, partial acceptance, reflection; attach additional sheet if necessary.)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| 12. Government Actions: (Reduced payment, cure notice, show cause, other)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| 13. Close Out |
|  | Name | Title | Signature | Date |
| ContractorNotified |  |  |  |  |
| b. COR |  |  |  |  |
| c. CO |  |  |  |  |